## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0009 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2624 |  |  | Transmital Date: 3/6/2024
Document Title: P&ID - 2nd Stage Gas Compression Suction Drums |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2624 |  |  | Transmital Date: 3/6/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0009_D08 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1403-2294-78133 | 1403/02/30 | مورد تایید می باشد.
2 |  |  | 1403-2294-78133 | 1403/02/30 | در طراحی اولیه به دلیل احتمال نیاز پکیج کمپرسور به استفاده از مسیر تخلیه در صورت Depressurizing امکان دسترسی به شیر BDV با یک سولونویید اضافه که به UCP پکیج متصل است دیده شد. همچنین وضعیت این شیر علاوه بر سیستم کنترل کارخانه به UCP پکیج نیز ارسال میشد که در صورت نیاز میتواتست در لاجیک راه اندازی پکیج استفاده شود.این موارد در نسخه های اولیه مدرک P&ID به وضوح نشان داده شده وبه اطلاع کارفرمای محترم رسیده است . در این نسخه از مدرک با توجه به انجام مطالعات HAZOP مربوط به پکیج کمپرسورو اعلام رسمی سازنده به اینکه امکان راه اندازی بدون تخلیه را داراست و نیاز به اتصال به شیر BDV ندارد ، اتصال این ادوات به UCP حذف شده است
3
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: