## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-EL-MR-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2122 |  |  | Transmital Date: 5/20/2023
Document Title: PMR For Transformers |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-EL-TR-2122 |  |  | Transmital Date: 5/20/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-EL-MR-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به نهایی شدن مدرک لیست بارها در واحد تراکم گاز، مقتضی است این مدرک بر اساس لیست بار نهایی به روز و اصلاح گردد. |  | 1402-2294-95481 | 1402/03/11 | مطابق با صورتجلسه مورخ 1403/05/14 در دفتر آن کارفرمای محترم و همچنین ترنسمیتال شماره 2764، ترانس 1250 کیلوولت آمپر کفایت خواهد کرد. بر همین اساس پیشنهاد مالی از سازندگان مختلف دریافت گردید و این مدرک به روزرسانی شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: