## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-EL-MR-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2122 |  |  | Transmital Date: 5/20/2023
Document Title: PMR For Transformers |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-EL-TR-2122 |  |  | Transmital Date: 5/20/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-EL-MR-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | No Comment. Note: "Spare Part List and Interchangeability Record" form shall be added to this document as attachement. Meanwhile following documents shall be added as reference documents in section 11.1 LIST OF REFERENCE / APPLICABLE DOCUMENTS: -Specification For Painting -Document Numbering Procedure -Existent MV Switchgear Expansion Single Line Diagram -LV Switchgear/MCC Single Line Diagram -Electrical Overall Single Line Diagram |  | BK-SUR-ENG-ELE-01-05506 | 2022-08-23 | مدرک شماره 13 از پیوست مربوط به Spare part List می باشد. دیگر مراجع نیز در مدرک اضافه گردید. |  |  | Noted and Closed.
2 | No Comment. Note: In case of any changes in prerequisite documents such as load list that lead to the transformer sizing, this document shall be revised. |  | BK-SUR-ENG-ELE-01-06381 | 2022-12-11 | در صورت هر گونه تغییر در مدرک لیست بار، این مدرک به روزرسانی خواهد شد. |  |  | Will be checked later.
3 | No Comment. |  | BK-SUR-ENG-ELE-02-07758 | 2023-05-30 | مطابق با صورتجلسه مورخ 1403/05/14 در دفتر آن کارفرمای محترم و همچنین ترنسمیتال شماره 2764، ترانس 1250 کیلوولت آمپر کفایت خواهد کرد. بر همین اساس پیشنهاد مالی از سازندگان مختلف دریافت گردید و این مدرک به روزرسانی شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: