## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0006 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2247 |  |  | Transmital Date: 7/17/2023
Document Title: Mechanical Data Sheets For Discharge Gas K.O. Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-2247 |  |  | Transmital Date: 7/17/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0006_D03 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | اطلاعات داده برگ های مکانیکی با داده برگ های فرآیندی در تناقض می باشدو به عنوان مثال می توان به سایز نازل PSV اشاره کرد |  | 1402-2294-228446 | 1402/06/11 | آخرین ویرایش مدرک مطابق آخرین ویرایش مدرک Process Data Sheet اصلاح و ارسال می گردد.
2 | میزان خوردگی مجاز در مدرک درج گردد |  | 1402-2294-228446 | 1402/06/11 | با توجه به CLAD بودن مخزن خوردگی برای مخزن در نظر گرفته نشده است
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: