## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0008 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2420 |  |  | Transmital Date: 10/10/2023
Document Title: Mechanical Data Sheets For Instrument Air Receiver |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-2420 |  |  | Transmital Date: 10/10/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0008_D02 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به عدم ارسال مدرک تایید شده میزان مصرف هوا و کاهش ابعاد مخزن نسبت به ویرایش اولیه مدرک و همچنین استناد پیمان ضروری است دلایل توجیهی جهت بررسی و تصمیم گیری اعلام گردد. |  | 1402-2294-344945 | 1402/08/28 | ابعاد مخزن مطابق آخرین ویرایش مدرک process data sheet اصلاح شده است در خصوص میزان مصرف هوا این مورد در مدرک مربوطه به کارفرما محترم اعلام می شود.
2 | علت تغییر اطلاعات SEISMIC DESIGN نسبت به ویرایش قبل اعلام گردد. |  | 1402-2294-344945 | 1402/08/28 | در ویرایش جدید مدرک اصلاح شده است
3 | فشار تست هایدرو استاتیک می بایست بر اساس استاندارد طراحیIPS-G-ME-150 در مدرک درج گردد. |  | 1402-2294-344945 | 1402/08/28 | در ویرایش جدید مدرک اصلاح شده است
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: