## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0012 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2247 |  |  | Transmital Date: 7/17/2023
Document Title: Mechanical Data Sheets For Flare K.O. Drum |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-ME-TR-2247 |  |  | Transmital Date: 7/17/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0012_D02 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | اطلاعات داده برگه های مکانیکی با برگه های فرآیندی در تناقض می باشد به عنوان مثال می توان به فشار طراحی اشاره کرد. |  | 1402-2294-228446 | 1402/06/11 | مدرک مطابق آخرین ویرایش Process data sheet اصلاح شده
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: