## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0014 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2421 |  |  | Transmital Date: 10/10/2023
Document Title: Mechanical Data Sheets For Slug Catcher |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-2421 |  |  | Transmital Date: 10/10/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0014_D02 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | استانداردIPS-D-ME-140 ارتباطی با این تجهیز ندارد و می بایست استانداردIPS مربوطه درج کد طراحی ذکر گردد. |  | 1402-2294-330974 | 1402/08/18 | این مورد اصلاح شد
2 | همانطور که در نامه شماره 02/2294/335846 مخازن باید داری Demister pad باشد و توضیحات ارائه شده در Reply Sheet پذیرفته نیست |  | 1402-2294-330974 | 1402/08/18 | Demister pad برای مخزن در نظر گرفته شده است به نوت 44 و sketch مخزن رجوع شود
3 | علت تغییر استاندارد باد و زلزله نسبت به ویرایش قبل مشخص گردد. |  | 1402-2294-330974 | 1402/08/18 | این مورد مطابق اسناد پروژه اصلاح شد
4 | سامانه پوشش داخلی مخزن به spec مربوطه ارجاع گردد |  | 1402-2294-330974 | 1402/08/18 | این مورد اصلاح شد
5 | یادداشت 11 در خصوص محل اتصال stand pipe بر روی تجهیز دارد لذا توضیحات ارائه شده در Reply sheet پذیرفتنی نیست |  | 1402-2294-330974 | 1402/08/18 | این نوت مجدد به مدرک اضافه شد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: