## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2247 |  |  | Transmital Date: 7/17/2023
Document Title: Mechanical Data Sheets For Inlet Gas K.O. Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-2247 |  |  | Transmital Date: 7/17/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0001_D03 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در اين مقطع زماني نقطه نظر خاصي مطرح نمي باشد، لذا مي بايست صرفا نقطه نظرات ذينفع اصلي پروژه اعمال گردد. |  | BK-SUR-ENG-MEC-02-08167 | 2023-07-25 | آخرین ویرایش مدرک مطابق آخرین ویرایش مدرک Process Data Sheet اصلاح و ارسال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: