## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2263 |  |  | Transmital Date: 7/24/2023
Document Title: PMR For Pressure Vessels |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-2263 |  |  | Transmital Date: 7/24/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0003_D02 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
QC comments :
1 | در بند 12.3، در جمله Scope of supply and work shall be fully based on Scope of supply and work in this Material Requisition (Attachment 1).، عبارت (Attachment 1) حذف گردد. |  | BK-SUR-ENG-MEC-01-05750 | 2022-09-24 | این بخش (با توجه به توضیحات غیر ضروری) حذف گردید.
2 | در اين برهه نقطه نظر خاصي مطرح نمي باشد . صرفا مي بايست نظرات احتمالي ذينفع اصلي پروژه بر روي اين مدرك اعمال گردد. همچنين لازم به ذكر است كه مسئوليت بروزرساني ويرايش مدارك پيوست مندرج در اين مدرك ، پس از نهايي شدن آنها ، بر عهده آن پيماكار مي باشد. |  | BK-SUR-ENG-MEC-02-08181 | 2023-07-26 | با توجه به بروز رسانی مدارک پیوست MR و پیش برد فرآیند خرید مدرک به همراه آخرین ویرایش پیوست ها ارسال می گردد.
3 | در بند 11 نام مدرك بصورت صحيحE&C-QC-SP-1 درج گردد. |  | BK-SUR-ENG-MEC-02-08234 | 2003-08-05 | این مورد در مدرک اصلاح شد.
4 | در بند 6 : عبارت " CLIENT and EPC/EPD (GC) CONTRACTOR" جايگزين عبارت ‌"Client/EPC Contractor"گردد. |  | BK-SUR-ENG-MEC-02-08234 | 2003-08-05 | این مورد به نحو مقتضی اصلاح گردید.
5 | در جدول Attachment 1 ، در رديف General Document & Procedures ، شماره مدرك بصورت E&C-QC-SP-1 آورده شود. |  | BK-SUR-ENG-MEC-02-08234 | 2003-08-05 | این مورد در مدرک اصلاح شد.
6 | در جدول Attachment 2 : 1- Painting Operator Certification Record اضافه گردد. |  | BK-SUR-ENG-MEC-02-08234 | 2003-08-05 | این مورد در مدرک اصلاح شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: