## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-EL-MR-0004 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1977 |  |  | Transmital Date: 3/28/2023
Document Title: PMR For Emergency Diesel Generator |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-EL-TR-1977 |  |  | Transmital Date: 3/28/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-EL-MR-0004_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
EL. Comments.
1 | In case of any changes in prerequisite documents, this document shall be revised. |  | BK-SUR-ENG-ELE-02-07316 | 28/03/2023 | مدرک محاسبات دیزل با ویرایش سوم و با ترنسمیتال شماره 2781، ارسال شده است. در صورت تغییر مجدد ظرفیت دیزل، این مدرک به روزرسانی خواهد شد.
2 | Emergency diesel generator main parts/accessories such as diesel engine, alternator, battery, charger, daily fuel tank, local control panel, first filling shall be mentioned in part 5.1 scope of supply. |  | BK-SUR-ENG-ELE-02-07316 | 28/03/2023 | اضافه گردید.
3 | local control panel schematic wiring diagram and single line diagram shall be added to attachment 2, Vendor min. documents requirements table. |  | BK-SUR-ENG-ELE-02-07316 | 28/03/2023 | اضافه گردید.
QC. Comments.
1 | در بند 6: -عبارت "QC Plan" و "Quality Control Plan" به "Inspection and Test Plan (ITP)" تغيير يابد. |  | BK-SUR-ENG-ELE-02-07316 | 28/03/2023 | اعمال گردید.
2 | لزوم ارائه مدارك ITP, QCP, MPS توسط سازنده قبل از برگزاري جلسه PIM در مدرك درج گردد. |  | BK-SUR-ENG-ELE-02-07316 | 28/03/2023 | مدارک ذکر شده، همگی جز پیوست های قرارداد می باشد که به هنگام عقد قراداد با برنده مناقصه، منظور خواهد شد. لذا جهت یکپارچگی بین تمامی MR ها از آوردن آنها صرف نظر شده است.
3 | در پيوست 2: - مدارك WPS & PQR, Final Data Book Index, Final Data Book, SAT Procedure اضافه شود. - در انتهاي جدول عبارت " List of Documents Will be Finalized in Vendor Document index and Schedule" به عنوان نوت اضافه گردد. |  | BK-SUR-ENG-ELE-02-07316 | 28/03/2023 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: