## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-HV-PY-0014 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2526 |  |  | Transmital Date: 1/1/2024
Document Title: HVAC System Layout & For Extension of Existing Control Building |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-HV-TR-2526 |  |  | Transmital Date: 1/1/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-HV-PY-0014_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مشخصات کولر ها و هواکش ها پس از اصلاح مدرک محاسبات در نقشه قید گردد. |  | 1402-2294-487095 | 1402/11/25 | بر اساس ابلاغ نهایی مبنی بر پیش بینی سیستم متمرکز HVAC، مدرک HVAC System Layout & For Extension of Existing Control Building به کلی بازبینی شد. مشخصات تجهیزات اصلی در مدرک Data Sheets For Main HVAC Equipment ارائه شده است.
2 | فضای dining room که در مدرک محاسبات به آن اشاره شده در نقشه مشخص گردد. |  | 1402-2294-487095 | 1402/11/25 | کلیه فضاها شماره گذاری شده اند. همچنین جدول شماره فضاها در مدرک ارائه شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: