## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-EL-DG-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2385 |  |  | Transmital Date: 9/25/2023
Document Title: Electrical Typical Schematic Diagrams For LV panel |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-EL-TR-2385 |  |  | Transmital Date: 9/25/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-EL-DG-0002_D07 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | صفحات 18 و 19 و 20 اضافه شده در این ویرایش ، از مدرک حذف گردند . مدار کنترل تابلوی برق پکیج ها در مدرک سازنده بررسی خواهد شد. |  | 1403-2294-185186 | 1403/05/16 | با توجه به اینکه وندور می بایست در پیشنهاد فنی خود، تمامی نیازمندی های پروژه را لحاظ نماید، لذا نیاز است که حتما این تیپیکالها در مدرک وجود داشته باشد. تا وندور بر اساس آن قیمت را در نظر بگیرد.
2 | براساس تعهدات پیمانکار و جهت پیشبرد پروژه ضمن رعایت ملاحظات شامل نظرات پیشین ، مدرک مرتبط و استاندردها ، استفاده از مدرک جهت اخذ پیشنهاد فنی بلامانع است ، لذا در مقطع طراحی و ساخت تابلوها نظرات تکمیلی ارائه خواهد گردید. |  | 1403-2294-185186 | 1403/05/16 | مورد تأیید است
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: