## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-DG-0005 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2591 |  |  | Transmital Date: 2/21/2024
Document Title: Control System/ESD system Loop Diagram |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-2591 |  |  | Transmital Date: 2/21/2024
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-IN-DG-0005_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به بند 13 قرارداد و نوع مدرك مسئوليت تعداد و نوع تجهيزات به كار رفته از نظر مالي و زماني بر عهده پيمانكار (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-02-08553 | 2023-10-04 | ملاحظه گردید.
2 | با توجه به تغييرات ارائه شده در جلسه HAZOP/SIL/HAZID موارد مجددا بررسي و ارسال گردد. |  | BK-SUR-ENG-INS-02-08553 | 2023-10-04 | با توجه به جلسه HAZOP/SIL/HAZID و مطابق آخرین نسخه از مدرک P&ID مدرک بروز رسانی گردید.
NEW COMMENTS
1 | با توجه به بند 13 قرارداد و نوع مدرك مسئوليت تعداد و نوع تجهيزات به كار رفته از نظر مالي و زماني بر عهده پيمانكار (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-02-08191 | 2023-07-30 | ملاحظه شد. |  |  | بسته شد
2 | كامنت هاي بخش ابزاردقيق به پيوست ارسال مي گردد. |  | BK-SUR-ENG-INS-02-08191 | 2023-07-30 | اصلاح شد. |  |  | بسته شد
4 | با توجه به نقطه نظرات بر روي اين مدرك و ديگر مدارك ترانسميتال، ترانسميتال فوق عودت داده مي شود لذا رويژن بعدي اين مدرك، با همين نسخه و همين ترانسميتال جايگزين گردد. |  | BK-SUR-ENG-INS-02-08191 | 2023-07-30 | انجام شد. |  |  | بسته شد
D01(Replace)
1 | در این مقطع نقطه نظر خاصی مطرح نمی باشد. در صورت تغییر در هر کدام از مدارک مرتبط در این مدرک نیز در نظر گرفته شود. |  |  | 2023-10-02 | ملاحظه گردید و انجام خواهد شد.
D02
1 | نقطه نظرات ذینفع اصلی بر روی مدرک در نظر گرفته شود |  | BK-SUR-ENG-INS-02-09085 | 2024-03-06 | انجام شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: