## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-EL-CN-0005 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2136 |  |  | Transmital Date: 5/28/2023
Document Title: Calculation Note For DC Charger System |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-EL-TR-2136 |  |  | Transmital Date: 5/28/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-EL-CN-0005_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | شارژر 24 VDc با توجه به عدم تأیید مدارک power Consumption توسط بخش ابزاردقیق از ارسال مدرک با ویرایش جدید خودداری گردد. |  | 1402-2294-133121 | 1402/04/06 | مطابق با صورتجلسه مورخ 1403/05/14 در اهواز، ظرفیت بارهای AC UPS و DC UPS مشخص گردید. همچنین مدرک لیست بارهای ابزاردقیق با ترنسمیتال شماره 2751 برای آن کارفرمای محترم ارسال شده است. در نتیجه آخرین محاسبات مدرک UPS با لیست بار ابزاردقیق همخوانی دارد. و به روزرسانی شده است.
2 | شارژر 110 ولت: ضروری است توان سیستم 110 ولت، بر اساس اسناد پایه برای خروجی 15 کیلووات بازنگری گردد |  | 1402-2294-133121 | 1402/04/06 | توان بر اساس آخرین لیست بار مورد نیاز به روزرسانی شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: