## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DT-0011 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2604 |  |  | Transmital Date: 2/27/2024
Document Title: Process Data Sheets For Elevated Potable Water Tank |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2604 |  |  | Transmital Date: 2/27/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0011_D05 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | ظرفیت مربوط به مخزن با توجه به آخرین ویرایش مدرک PID می بایست در داده برگ قید گردد، لذا با اعنال بند فوق در این مقطع نقطه نظر خاصی مطرح نمی باشد وپیشبرد فاز بعدی مهندسی بلامانع می باشد. |  | 1402-2294-545667 | 1402/12/28 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: