## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-ME-DW-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1599 |  |  | Transmital Date: 11/23/2022
Document Title: Standard Detail Drawing For Storage Tanks |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-ME-TR-1599 |  |  | Transmital Date: 11/23/2022
[5 empty] | CRS No: NISOC-CRS-BK-GNRAL-PEDCO-000-ME-DW-0002_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | شایان ذکر است محتوای مدرک ارسالی پیشتر طی نامه 01/2294/216173مورد پاسخ قرار گرفته است. مزید اطلاع اعلام می گردد که این مدرک با وضعیت FI (POI) ارسال شده و مغایر با روش هماهنگی فی مابین می باشد. از اینرو ضروریست تا در اسرع وقت مورد اصلاح قرار گیرد. |  | 1401-2294-369331 | 1401/09/30 | با توجه به تایید شدن مدرک در ویرایش D01 لذا مدرک D02 با وضعیت FI برای کارفرما محترم ارسال شده است. به پیوست مدرک تایید شده ویرایش D03 ارسال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: