## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ST-CN-0027 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-2587 |  |  | Transmital Date: 2/19/2024
Document Title: Calculation Note For CCTV Control Room- Binak GCS |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ST-TR-2587 |  |  | Transmital Date: 2/19/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ST-CN-0027_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1402-2294-530155 | 1402/12/20 | عطف به نامه شماره 03/2294/96124 مورخ 1403/03/12 کارفرمای محترم نیازی به ضدانفجار بودن ساختمان مذکور نمی باشد
2 |  |  | 1402-2294-530155 | 1402/12/20 | مدرک AFC ارسال می گردد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: