## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-TB-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1661 |  |  | Transmital Date: 12/6/2022
Document Title: TBE For Pressure Vessels |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-1661 |  |  | Transmital Date: 12/6/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-TB-0003_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date |  |  |  | Client Conclusion
1 | تقطيران : Data Sheet براي مخازن ارايه نشده است. در Technical Offer ارائه شده PWHT در نظر گرفته نشده است. وضعيت گارانتي ارائه شده با مدرك MR تناقض دارد. |  | BK-SUR-ENG-MEC-01-06561 | 2022-12-30 | با توجه به دریافت مجدد پیشنهاد فنی از سازندگان - شرکت تقطیران پیشنهاد فنی مجدد برای شرکت در مناقصه ارسال نکرده. لذا از فرآیند خرید کنار گذاشته شده است
2 | تهران جوان: وضعيت گارانتي با مدرك MR داراي تناقض مي باشد،شفاف سازي گردد. ضخامت مخازن در Technical offer با مدرك Data Sheet ارائه شده توسط Vendor تناقض دارد. |  | BK-SUR-ENG-MEC-01-06561 | 2022-12-30 | به پیوست آخرین ویرایش از پیشنهاد فنی شرکت تهران جوان ارسال می گردد.
3 | General Comment: - Sub Vendor List shall be based on NISOC Approved Vendor List - Vendor’s preliminary quality plan & ITP - Vendor shall confirm that project PMS will be followed for all pipes, valves, gaskets, etc. and -Specification For Lining (Internal Protection of Equipment by Painting) DOC. NO." BK-GNRAL-PEDCO-000-PI-SP-0007"shall be followed for all vessels internal coating |  | BK-SUR-ENG-MEC-01-06561 | 2022-12-30 | Noted
4 | All internal & external welded parts to the equipment such as baffle ,vortex breaker, support Clips, lugs, or rings for insulation and fire proofing and etc. are in vendor’s scope of supply. |  | BK-SUR-ENG-MEC-01-06561 | 2022-12-30 | Noted
5 | Gaurantee and warantee terms shall be according to MR. |  | BK-SUR-ENG-MEC-01-06561 | 2022-12-30 | Noted
6 | All documents required after purchase order shall be submitted in accordance with vendor documents requirements of the PMR. |  | BK-SUR-ENG-MEC-01-06561 | 2022-12-30 | Noted
| در خصوص sub vendor معرفي شده شركت تقطيران براي Material تنها شركت هاي ذيل مورد تاييد مي باشد و از ساير شركت ها هيچ گونه اطالاعاتي يافت نگرديد: Carbon steel plate : Dillinger/salzgiter-Posco-Foolad Mobarakeh/Oxinsteel Stainless steel plate : Bao Steel-Tisco Pipe: Tubacex-Jiuli Co |  | BK-SUR-ENG-MEC-01-06561 | 2022-12-30 | با توجه به دریافت مجدد پیشنهاد فنی از سازندگان - شرکت تقطیران پیشنهاد فنی مجدد برای شرکت در مناقصه ارسال نکرده. لذا از فرآیند خرید کنار گذاشته شده است
7 | شركت گروه صنعتي تاكستان به شماره شناسه ملي 10861638467 مطابق با اخرين بروز رساني ( 05/10/1401) در مرحله ارزيابي در فهرست بلند مي باشد ( خود اظهاري) و مورد تاييد نمي باشد . |  | BK-SUR-ENG-MEC-01-06561 | 2022-12-30 | با توجه به دریافت مجدد پیشنهاد فنی از سازندگان - شرکت تاکستان پیشنهاد فنی مجدد برای شرکت در مناقصه ارسال نکرده. لذا از فرآیند خرید کنار گذاشته شده است
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: