## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-MR-0020 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-2561 |  |  | Transmital Date: 2/5/2024
Document Title: PMR For LBV |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-2561 |  |  | Transmital Date: 2/5/2024
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-IN-MR-0020_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-02-08960 | 2024-01-22 | ملاحظه شد |  |  | بسته شد
2 | مدرک Spec و Datasheet نهایی نبوده و این مدرک قابلیت نهایی سازی را ندارد. |  | BK-SUR-ENG-INS-02-08960 | 2024-01-22 | مدرک با اخرین مدرک Spec و Data sheet اصلاح شده مطابق نظر کارفرمای محترم، جهت بررسی ارسال میگردد. |  |  | باز است. مدارک پیش نیاز نهایی نمی باشند.
D01
2 | در صورت تایید مدارک پیش نیاز از نظر محتوای MR، نقطه نظر خاصی مطرح نمی باشد. |  | BK-SUR-ENG-INS-02-09025 | 2024-02-17 | مدرک مطابق آخرین نسخه از مدارک پیش نیاز تهیه گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: