## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0010 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2758 |  |  | Transmital Date: 8/19/2024
Document Title: PMR For Centrifugal Pumps For General Services |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-2758 |  |  | Transmital Date: 8/19/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0010_D04 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | همانگونه که در نامه های شماره 03/2294/100338، 01/2294/231560،02/2294/201743 و 01/2294/371137 بیان گردیده است، ساختار کلی مدارک مورد تایید بوده و لیکن ارسال نسخه بعدی مدارک فوق منوط به نهایی سازی کلیه مدارک مرتبط مهندسی و درج نسخ تایید شده (AFC) خواهد بود. لذا صدور نسخه جدید مدرک در حالی که مدارک پیشنیاز به طور کامل نهایی نشده است توجیه پذیر نبوده و تنها سبب مکاتبات مضاعف خواهد بود. در ضمن مزید تاکید اعلام میگردد از آنجا که مسئولیت طراحی تفضیلی پروژه جزو تعهدات پمیانکار پروژه بوده و همچنین با استناد به وضعیت مدرک ارسالی (IFI)، مسئولیت کامل عدم تطابق متریال مندرج در این مدرک (مشخصات فنی و یا تعداد) در مرحله سفارش گزاری و خرید بر عهده آن پیمانکار بوده و از اینرو پیشبرد گام بعدی امکانپذیر است. |  | 1403-2294-218523 | 1403/06/10 | با توجه به اینکه پیوست مدارک مرتبط مهندسی نهایی شده است مدرک با وضعیت FI ارسال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: