## Mechanical- rev 01
نگهداشت و يش توليد ميدان نفتي بينك سطح الارض احداث رديف تراكم گاز در ايستگاه جمع آوري بينك
Mechanical Deviation / Clarification List
|  |  | 12.07.2022 |  | Rev. 00
Item No. | Document No. | Specification Clause No. | Specification Requirements | D/C/E | Deviation / Clarification | Contractor Comments
1 | Mechanical Design Criteria | 3.1 LOCAL CODES AND STANDARDS (LATEST REVISION) | General | D/C | Please refer to HAVAYAR applicable codes and standards. | All of the standards specified in mechanical design criteria shall be followed by vendor for whole of the package. HY Reply: Not accepted, Havayar's applicable code and standard is considered for itmes mentioned in this document.
2 |  | 6.19 SAFETY MEASURES | Ladders and platforms for equipment: | D | Please, be noted that ladder and platform is not applicable for air dryer, nitrogen generator, air and N2 receivers due to the small size of towers. | Vendor shall confirm to supply and work of equipment insulation if required. HY Reply: Insulation is not applicable.
3 |  | 8.3 INSULATION | Above ground equipment and piping shall be insulated for the conservation of heat and protection of personnel as indicated on the line list and/or the equipment data sheets or P&IDs. | D | Not requiered. | Noted.
4 | PMR FOR INSTRUMENT/PLANT AIR & NITROGEN PACKAGES | 5.1 SCOPE OF SUPPLY for the Air Compressors | Foundation bolts (anchor bolt), skid leveling screws, shims, sub-plates | D | Anchor bolt will be supplied by Havayar. | Noted.
5 |  |  | Inlet filter (auto cleaning type) | D/C | Please be noted that inlet filter of compressor is cartridge type and will be changed when compressor is shut down, so auto cleaning type is not applicable in screw compressor. | Not accepted, to be followed by vendor. HY Reply: Not accepted, self celaning filter is not applicable for screw compressors. The filters are cartridge-type and can be easily replaced when the compressor is turned off.
6 |  |  | o Blow off silencer o Inlet silencer o Inlet IGV | D/C | Please be noted that 1ST stage discharge,2ND stage discharge and blow down valve silencer have been considered. IGV is not applicable for screw type compressor. | Noted
7 |  |  | Manifolded single connections at the edge of skid for utility connections & drain and vent connections | C | Drain tie- in point is at the edge of skids (if required and practical), be noted that since vent fluid is air and is routed to ATM, so it is not required to gather vent line to one point. | Noted
8 |  |  | Surge drum | D/C | Vessel after compressor for instrument/plant air package and before N2 generator for nitrogen package has been considered for storage of the compressed air and prevents pulsation. | Noted
9 |  |  | Spare compressor shall be provided | C | The quantity of compressor has been considered based on item 2.GENERAL of "PMR FOR INSTRUMENT/PLANT AIR & NITROGEN PACKAGES" | Noted
10 |  |  | o Special tools for erection and maintenance o Capital spare parts (as option) | D/C | Special tools and capital spare parts are not applicable. | Vendor shall confirm to supply special tools if required. HY Reply: Confirmed, special tools are not applicable.
11 |  | 5.1 SCOPE OF SUPPLY for the Air Dryer Package | Air dryers beds (mole sieve adsorption type) (for each package one bed in adsorption and one bed in regeneration mode) | D | Accordign to our experince Molecularseive/Activated Alumina will be considered. | Noted.
12 |  |  | o Dual-pre-filters & dual-after-filters (Cartridge Element) with spares filters o Water trap for dual filters | C | Please be noted that dual filter(One operating and one spare) has been considered, separate spare filter is not applicable. o Mechanical Auto drain has been considered and since the compressed air is fully dry after the dryer, it is not required to consider auto drain for after filters. | Noted
13 |  |  | Manual globe valve and FT for regeneration line○ | D/C | Please be noted that due to the small size of air dryer adjustable purge is not applicable, so globe valve and FT will not be considered. | All valves and instruments in project P&ID shall be considered by vendor as minimum. HY Reply: Please refer to Havayar's P&ID.
14 |  |  | Common skid for all equipment in package | D/C | Please be noted that the whole package will not be delivered as one skid ,each compressor,air dryer,nitrogen Generato & chiller has its own skid, ,filters and water trap will be installed on piping, vessels will be supported with leg. | Noted.
15 |  |  | Anti-condensation heaters for motor | D/C | Not applicable for air dryer and N2 generator. | Noted, but please be noted that compressor with lube oil system console ( for its bearings) shall be on common skid.
16 |  | 5.1 SCOPE OF SUPPLY for the Nitrogen Package | check valve for Nitrogen Gaseous discharge line | D/C | VIP valve has been considered on discharge line of N2 Generator based on manufacturer design,check valve is not applicable . | Noted.
17 |  |  | Plan for HOLD points in the production process proposed to PURCHASER for witness or approval particular activities. | D/C | Please be noted that for equipments which are supplied from abroad ,accessing to shops and witnessing the tests are not possible. | All of the valves and instruments in purchaser's P&ID shall be considered by vendor at least. HY Reply: Please refer to Havayar's P&ID.
18 |  | ATTACHMENT 1 | LIST OF REFERENCE / APPLICABLE DOCUMENTS | C | VPIS will be finalized in the KOM after P.O. | Noted.
19 | SPECIFICATION FOR AIR COMPRESSOR PACKAGE | General | Whole of document | D/C | Compressor will be designed, fabricated and inspected based on manufacturer standard. | Noted.
20 | SPECIFICATION FOR PRESSURE VESSELS | 6.0 MATERIAL (IPS CLAUSE 7.1) | 7.1.1.1 All material used in the fabrication shall be new and have a minimum quality as specified in the requisition and shall be in accordance with ASME Sec.II Part D / ASTM specifications and standard. | D/C | All material will be based on ASTM/ASME, unless otherwise Equivalent material will be submitted after contract. Water trap & Filter material is based on European standard based on mfg standrad (OMEGA). | OMEGA is not in project AVL. HY Reply: Filter housing is ASME type and made by Havayar.
21 |  | Appendix N (Addition) | Nozzle Load table (as Min.) | D/C | Please be noted that Nozzle Load will be considered for inlet/outlet of dryer & N2 generator skid and for inter-skid of dryer and N2 generator is not applicable. | Not accepted, project requirements shall be followed by vendor. HY Reply: Not accepted, client external nozzle load will be followed at skid battery limit. Nozzle load will not be considered for inter skid of compressor, chiller, dryers, N2 generator, and filters and water trap. please refer to our agreement on TCL item No. 6 in MECHANIC FIX section.
22 | SPECIFICATION FOR AIR DRYER PACKAGES/SPECIFICATION FOR NITROGEN PACKAGE | 6.2 MECHANICAL DESIGN DATA | PSA air dryer is subject to the high cycle fatigue loads. FEA and ASME VIII-2 are necessary. |  | Please, be noted that since there is no any cycle load for air dryer and N2 generator,so Fatigue analysis is not applicable. | ??????? HY Reply: Please clarify.
23 |  |  | Each air dryer shall be complete with the Vendor’s standard twin coalescing pre-filters |  | Please be noted that filters are cartridge type. | Noted.
24 |  |  | The equipment shall be designed and fabricated to take into account the effect of direct exposure to solar radiation. | C | Please be noted that package has been considered outdoor-under shelter,supply of shelter is out of Havayar scope. | Noted.
25 |  |  | For all parts made of carbon steel, corrosion allowance of 3.2 mm and for the stainless steel material corrosion allowance of zero shall be considered. | D/C | Please,be noted that corrosion allowance 3 mm has been considered. | Not accepted, this requirement shall be followed by vendor. HY Reply: Confirmed, 3.2mm had been considered.
26 |  | 6.2.2 REGENERATION SYSTEM | In the event of a power failure, the dryer shall continue to dry the incoming air to the specified dew point for a minimum of one hour | D/C | Please be noted that In the event of a power failure compressor will be shut down and there is not any plant air and instrument air. | Not accepted, project requirements shall be followed by vendor. HY Reply: Not accepted, in the event of a power failure compressor will be shut down.
27 |  | 6.2.3 PRE- FILTRATION SYSTEMS AND AFTER FILTRATION SYSTEMS | filtration system design shall be in accordance with "Specification For Pressure Vessels; Doc. No. BK-GNRAL-PEDCO-000-ME-SP-0001 ", Codes and standards ASME VIII and IPS-G-ME-150(1). | D/C | Filters housing will be designed, fabricated and inspected based on manufacturer standard (OMEGA) , not ASME. | Noted.
28 |  |  | One operating and one standby activated carbon filters shall be provided, adequately sized to meet the flow conditions as stated in the material requisition data sheets | D/C | Please be noted that since oil free compressor has been considered, so activated carbon filters are not applicable. | Not accepted, project requirements shall be followed by vendor. HY Reply: Activated carbon filters are not applicbale as compressor is oil-free type.
29 |  | 6.2.4 MATERIAL | The skid shall be fabricated from structural steel | D/C | Please be noted that there is not any steel structure in this package, skid has been considered for dryer and N2 Generator which is based on manufacturer standard and design | The skid shall be fabricated from structural steel
30 |  | 6.2.5 PIPING AND CONNECTIONS | The structural analysis for the structure and stress analysis for piping within the skid (NPS 6" and more) shall be design as per project documents. | D/C | Stress analysis for inter-skid of dryer and N2 generator is not applicable. Inter-skid design of dryer and N2 generator is as per vendor design. | Noted.
31 | PROCESS DESIGN CRITERIA | 4.2.9 Drains, Vents and Steam-Out Connection | Vent, Drain and Steam-out Connection shall be defined as follows: V < 45, D < 1200 Vent= 1 1/2" Drain=1 1/2" | D/C | Please be noted that size of drain connections for filter and water trap is considered 1/2" and threaded. Also, vent is not applicable for Filters and water trap. Vent and drain is not applicable for air dryer and nitrogen generator. | Noted.
32 |  | 4.2.6 Manway Sizes | Under 900 mm ID: Top head flanged 900 to 1300 mm ID: Man way, in shell, 20” ID | D/C | Diameter of tower air dryer is so small to install of manhole/ hand hole. Therefore there is not any opening such as handhole or manhole on towers.Body flange will not be considered, Two connections for charging and discharging molecular sieve at the top and bottom of the tower are considered. For nitrogen generator towers , handhole 8" will be considered. Also, manhole 18" will be considered for Air and N2 Receivers which is sufficient since there is no internal inside of receiver | Noted.
33 | SPECIFICATION FOR PAINTING/SPECIFICATION FOR LINING (INTERNAL PROTECTION OF EQUIPMENT BY PAINTING) | General | Whole of document | D/C | Project painting specification and also RAL code will be followed for all equipment except filters ,water trap, chiller and valves which are based on manufacturer standard. Thickness and type of paint is according to this spec, procedure will be followed according to Havayar's procedure which will be sent in detail design stage. | Noted.
34 | PIPING CORROSION STUDY & MATERIAL SELECTION REPORT/PIPING MATERIAL SPECIFICATION/SPECIFICATION FOR THE DESIGN OF PIPING IN MECHANICAL PACKAGES/SPECIFICATION FOR METALLIC PIPES/SPECIFICATION FOR MANUAL VALVES/SPECIFICATION FOR PLANT PIPING SYSTEMS PRESSURE TESTING/SPECIFICATION FOR WELDING OF PLANT PIPING SYSTEM & NDT/SPECIFICATION FOR FITTINGS, FLANGES, GASKETS AND BOLTS/PIPING DESIGN CRITERIA/SPECIFICATION FOR PIPING CLEANING AND FLUSHING | General | Whole of document | D/C | Please be noted that project PMS and piping spec is not applicable for piping inside of the air compressor skid, chiller, air dryer skid and nitrogen generator skid. Piping inside of skid will be based on manufacturing standard. PMS will only be followed at B.L. of skids. Be noted that piping between skids/Equipment will be supplied as loose item by Havayar, installation and pipe work is out of Havayar scope. Please be noted that valves including ball valves and check valves inside the air dryer skid and also VIP valves and angle seat valves inside the N2 generator skid will be selected based on HAVAYAR's Know-How and valve spec and PMS can't be followed. Valve material of instrument air has been considered same as plant air (piping class AN04). | Piping
35 | SPECIFICATION FOR MATERIAL REQUIREMENTS IN SOUR SERVICE | General | Whole of document | D | Not applicable. | Noted.
36 | دستورالعمل پرتونگاري و سایر آزمایشات غیر مخرب/دستورالعمل جامع بازرسی خرید و ساخت کالا/دستورالعمل انتخاب سطح بازرسي كالا و تجهيزات | General | Whole of document | D/C | Project ITP will be followed for receivers and vessel of dryers and N2 generators. ITP of compressor, chiller, filters and water trap are based on manufacturer standard. ITP will be finalized after P.O. and in PIM. | Noted.ITP of compressor, chiller, filters and water trap are based on manufacturer standard. ITP will be finalized after P.O. and in PIM.
37 | SPECIFICATION FOR COLOR CODING AND MARKING/PACKING , MARKING , TRANSPORTATION PROCEDURE | General | Whole of document | D/C | Export and seaworthy packing are not applicable. Packing is valid for 6 months and shall be changed after this time period. | Noted.
38 | New Item | SPECIFICATION FOR CONCRETE WORK | Whole of document |  | .Civil works is out of HAVAYAR scope | Noted.
Some General Deviation & Notes: 1. Please be noted that piping between skids/Equipment will be supplied as loose item by HAVAYAR ,pipe work and installation is out of Havayar scope. 2. Please be noted that package has been outdoor-under shelter,supply of shelter is out of Havayar scope. 3. Please be noted that filters and water trap are generally designed and fabricated based on their manufacturer standard, not ASME, and also their body material is Aluminium. 4.Civil works is out of HAVAYAR scope. 5.Crane is out of scope of Havayar. 6.HAVAYAR's scope of work is according to attached P&ID. 7. Deleted. 8. Please be noted that all of On-Off valves are based on manufacturer standard .
D : Deviation C :Clarification E : Exception

## Process- rev 01
Deviation List
|  |  | 11.03.2024 |  | Rev 01
Item No. | Document No. | Specification Clause No. | Specification Requirements | D/C/E | Deviation / Clarification | Contractor Comments
1 | BK-GCS-PEDCO-120-ME-MR-0006-01 | GENERAL | GENERAL | D/C | Please be noted that the nitrogen generation package includes one compressor, one closed loop chiller, one air dryer package, and one PSA unit for N2 generation. It should be mentioned that the design is according to attached P&ID.
2 |  | LIMITS OF SUPPLY | For the Air Compressors | D/C | Please be noted that there is a PT in the discharge line of each compressore package, also it should be mentioned that load sharing is not applicable for screw compressors.
3 |  |  | For the Air Compressors | D | Considering "PDT for inlet Air Filters", please be noted that the design is according to the attached P&ID of screw compressor.
4 |  |  | For the Air Dryer Package | D | Based on "Manual globe valve and FT for regeneration line", please be noted that there is not any globe valve and FT in the dryer package lines.
5 |  |  | For the Air Dryer Package | D/C | Please be noted that mechanical auto drain has been considered in the packages.
6 |  |  | For the Nitrogen Package | D/C | Please be noted that there are not any analyzer for carbon dioxide and carbon monoxide content in the package, therefore, HAVAYAR does not guarantee this item.
7 |  |  | For the Nitrogen Package | D | Based on "H2O analyzer at discharge of air N2 Generator (at downstream of particulate filters)", it should be mentioned that there is not any H2O analyzer at the discharge line of N2 generator. Only O2 analyzer after N2 generator will be considered.
8 |  |  | MAIN DESCRIPTION | D | Deleted.
9 |  |  | MAIN DESCRIPTION | D/C | Please be noted that there is dew point transmiter on the downstream of air dryer and O2 analyzer at downstream of the N2 PSA package.
10 | BK-GCS-PEDCO-120-PR-SP-0002-04 | INSTRUMENT/PLANT AIR PACKAGE | Operating Case and Design Capacity | C | Based on the "Maximum demand: In which the total air demand ..." and regarding utilizing 15% of the dry air for regeration, inlet flow of the air dryer has been considered 140.8 Nm3/h. (10% over design will be considered for design of dryer)
11 |  |  | Operating Case and Design Capacity | C | Based on the "30 Nm3/hr will be considered as total consumption of wet plant air" flowrate of the plant air has been considered 30 Nm3/h.
12 |  |  | Operating Case and Design Capacity | C | Based on the mentioned demand of wet plant air and instrument air, 170.8 Nm3/h has been considered as air compressor capacity. (10% over design will be considered for design of dryer)
13 |  |  | Product Requirement | D/C | The pressure of produced instrument air and plant air are 9 barg and 9.5 barg, respectively. Please be noted that the minimum pressure of the produced instrument air has been considered 7 barg.
14 |  | NITROGEN PACKAGE | Design Basis | C | The flowrate of the produced N2 has been considered 34 Nm3/h with purity of 99.9% in 30 °C.
15 |  |  | SCOPE OF SUPPLY | D | Please be noted that there are not any TT, UV and check valve for nitrogen line.
16 |  | Design Basis | Design and Operating Condition | D/C | Deleted.
17 | BK-GCS-PETCO-120-PR-PI-0016 | P&ID - N2 GENERATION SYSTEM |  | D/C | Mechanical drain has been considered for the packages.
18 |  |  |  | D/C | Please be noted that N2 and air RECEIVER (after and before N2 generator) has been considered to damp the fluctuation and purity of produced N2.
19 | BK-GNRAL-HD-000-PR-DB-0001-08 | SITE CONDITION | BAROMETRIC PRESSURE | C | Please be noted that 14.37 psi (related to elevation of 180 m) has been considered as barometric pressure.
20 |  |  | AMBIENT CONDITIONS | C | Please be noted that 50 °C and 5°C have been considered as maximum and minimum ambient temperature, respectively.
21 |  |  | AMBIENT CONDITIONS | D/C | Please be noted that 100% has been considered as Max. relative humidity.
D : Deviation C :Clarification E : Exception

## I&C and Electrical-rev02
Electrical & Instrumentation CLARIFICTION and DEVIATIONES |  |  |  | نگهداشت و يش توليد ميدان نفتي بينك سطح الارض احداث رديف تراكم گاز در ايستگاه جمع آوري بينك |  | 12 Aug 2023 Rev02
Item No. | I&C/ ELEC. | Reference Document | DOCUMENT REQUIREMENT | D : Deviation E : Exception C : Clarification | VENDOR’S DEVIATION/EXCEPTION | PURCHASER ACCEPTANCE JUSTIFICATION
1 | Electrical | Scope of work | Scope of work | C | The electrical cable & route of them from client MCC(subsatation) to each compressor LCP is out of Havayar scope. Only the cable of on skid and cable from LCP of compressor to chiller LCP is by Havayar. The cable of compressor and chiller skid is PVC ,un armored according to Havayar standard. | Hirgan Reply: 1402-06-07. On Skid according to manufacture STD. Between skid according to Project specification. Refer to Item 6 of Electrical TCL. HY Reply: Confirmed
2 |  |  | Voltage level & Feeder | C | Feeder requirment is as below: - Instrument & Plant Air Package (PK-C-2203A) - Instrument & Plant Air Package (PK-C-2203B) - Nitrogen Package (PK-2204) Which will be connectted to compressor LCP. All feeders are fixed type and LCP are fix(No withdrawable). For UPS/Non UPS requirment for panel please refer to HAVAYAR submitted load list. | Hirgan Reply: 1402-06-07 Closed
3 |  | Data Sheets for LV Induction Motors | Note 1: IPS design margin is defined in accordance with standard output power rating of motor: 2 from 22kW to 55kW 1.15 | D | For motor sizing only site condition derate factor has been considered. | Hirgan Reply: 1402-06-07. Motor Sizing shall be according to API 617 & all requirement of process shall be considered. HY Reply: Confirmed
4 |  |  | 83 Terminal Boxes: [X] Power Terminal Box [X] Space heater (if required) | D | connection of PTC & Space heater (if required) will be considered in main terminal box of motor and separate terminal box will not be considered. | Hirgan Reply: 1402-06-07 Closed
5 |  |  | 43 Starting Method Direct on Line | D | Motor starter method is Start/Delta. | Hirgan Reply: 1402-06-07 Closed
6 |  |  |  | C | Package has been considered and design for safe area. All electrcal equipments are safe (Non-Ex TYPE). | Hirgan Reply: 1402-06-07 Closed
7 |  | Electrical Design criteria | 5.8 Degree of Protection outdoors installation IP 54 | D | LCP of compressor and chiller are as per manufacure design and standard. Chiller LCP is IP54(No certify). | Hirgan Reply: 1402-06-07 Closed
8 |  |  | - short circuit current of 50 kA - Ammeters will be provided for motors larger than or equal to 4 kW - Earth fault protection | D | LCP of compressor and chiller are as per manufacture design and standards. Earth fault protection is not apllicable. Ammeter only for main motor of compressor will be considered. | Hirgan Reply: 1402-06-07 According to IPS-E-EL-100, ammeter shall be considered for motor Above 4 KW. Protection shall be based on IPS. HY Reply: Confirmed
9 |  | MR FOR INSTRUMENT/PLANT AIR & NITROGEN PACKAGES | - Outdoor MCC for Auxiliaries Electrical Load (if any) | C | For compressor & Chiller motor starting panel is on skid LCP. | Hirgan Reply: 1402-06-07 Closed
10 |  |  | o Two earthing bars | D | one earth bar with two connection point will be considered for skid. | Hirgan Reply: 1402-06-07 Closed
11 |  |  | 5.4 BATTERY LIMITS c) Electrical - Incoming Power Supply of Local MCC - Incoming Power Supply of AC or DC UPS (if Any) - Earth Bosses on Skids | C | BATTERY LIMITS for electrical is edge of compressor LCP. Earthing only on skid is by HAVAYAR. | Hirgan Reply: 1402-06-07 Closed
12 | I&C | Scope of work | Scope of work | C | The I&C cable and route of them between skid/field & UCP, also between DCS & UCP are out of Havayar scope. Only the cable of on skid is by Havayar. The cable of skid is PVC, un armored according to Havayar design and standard. Cable between UCPs in air package is out of HAVAYAR scope.
13 |  | MR FOR INSTRUMENT/PLANT AIR & NITROGEN PACKAGES | o Outlet FT for surge control o Anti-surge controller for each compressor shall be considered. | D | surge control is not applicable for this type of compressor.
14 |  |  | - PlC based UCP, common for air compressor and dryer, located either on the skid package itself or remotely in the control building. UCP shall be connected to the PCS, ESD, for required monitoring, control functions and shutdowns as per P&ID. UCP panel door shall including alarm, trip and interlock logic; annunciator lamp and buzzer; push button switches; Terminal box, if UCP is control room mounted , required LCP for local command is required. - Package running status /common alarms/faults to be transferred to DCS via Air compressor UCP | D | Already 3 UCP (2 for air package and one for N2 package) has been considered. ESD system for ESD signal is not applicable. Panel maunted HMI 12''(No PC type) has been considered (on each UCP panel door). Chiller has a LCP and a Local microprocessor based Controller (No PLC type) as per manufacture design & standards. Control of comp., Dryer and N2 generator is via UCP which located in client control room. Interface with client cable on skid of compressor is LCP.
15 |  |  | For the Air Compressors: o PT,TT & FT on common discharge header of compressors for load sharing and load management o PDT for inlet Air Filters o LT for water separators o PT& TT for inlet and out let of each stage of compressor o PSV at discharge of each compressor | D | o load sharing is not applicable for this type of compressor therfore PT,TT & FT has not been considered on discharge line for load sharing. on discharge line of compressor PT has been considered.TT location is after second stage of compressor. o PT has been considered for inlet Air Filters as per manufacturer design. o Not applicable o As per HAVAYAR Design. o Not required for discharge. Required PSV for compressor has been considerd as per HAVAYAR Design. Instrumentation inter skid of compressor is as per HAVAYAR Design.
16 |  |  |  For the Air Compressors: o All transmitters shall transferred to DCS for operator monitoring purpose o Package running status /common alarms/faults to be transferred to DCS from UCP by MODBUS RTU | D | UCP will be connected to DCS via MODBUS TCP/RTU
17 |  |  | For the Air Dryer Package: o FT for regeneration line | D | o Not applicable
18 |  |  | o PDT for Air Dryer beds | D | As per client P&ID PDT for dryer bed has not been considered.
19 |  |  | o H2O analyzer at discharge of air N2 Generator | D | one dew point transmitter has been considered after dryer.
20 |  |  | TSV for gaseous nitrogen lines | D | Not applicable
21 |  | SPECIFICATION FOR INSTRUMENTATION | Transmitters shall be of the smart transmitter type with HART Integral digital indicators (local LCD indication) shall be supplied for each transmitter. Accuracy of Electronic transmitters: ±0.1% of calibrated span or better. | D/C | All transmitters inter skid of compressor and chiller are without HART and display with accuracy 0.5%. Dew point transmitter Accuracy is ± 3°C. HART is not applicable for dew point transmitter and O2 analyzer.
22 |  |  | MANIFOLD | D | Except for inter skid of compressor and chiller.
23 |  |  | Pressure gauges shall be solid front. Guaranteed gauge accuracy shall be within 0.6% of full scale range( | D | PGs are without solid front.
24 |  |  | minimum degree of protection shall be IP 65. | D | Except O2 analyzer accuracy is IP42 lacated in panel IP65.
25 |  |  | 6.1 CONNECTION ON PIPING AND EQUIPMENT | D | On skid of compressor and chiller Instrument process conection is threaded.
26 |  |  | 5.6 HAZARDOUS PROTECTION | C | Package has been considered and design for safe area. All instruments and equipments are safe (Non-Ex TYPE).
27 |  |  | The accuracy of the pressure switch assembly shall be at least 1% of the span Micro-switches shall be two double pole double throw (DPDT) type | D | Dryer PS is SPDT type.
28 |  | SPECIFICATION FOR INSTRUMENT AND CONTROL OF PACKAGE UNIT SYSTEM (PU) | Type A,B & C” Diagram |  | Already 3 UCP (2 for air package and one for N2 package) has been considered. ESD system for ESD signal is not applicable. Chiller has a LCP and a Local microprocessor based Controller (No PLC type) as per manufacture design & standards. Control of comp., Dryer and N2 generator is via UCP which located in client control room. Please refer to HAVAYAR submitted configuration diagram
29 |  | SPECIFICATION FOR PRESSURE SAFETY VALVES (PSV) | API RP-520 ASMEVIII | D | On skid of compressor and chiller PSV sizing is as per vendor standard and ASME or API will not be followed (threaded & body material is Brass). For between skid API will be followed.
30 |  | SPECIFICATION FOR ON OFF /SHUTDOWN VALVES (ESD/MOV) | General | D | Valve of N2 generator is special type & will be controlled with HDM block valve. VIP valve is without solenoid & limit switch. Material of HDM block valve is Aluminum. please Refer to attached file.
31 |  |  | limit switch & positioner | D | Dryer On/Off valves are without limit switch & position indicator.
32 |  | General | LCP IP | D/C | LCP of chiller is IP54(No certify) and as per manufacturer standard.
33 |  |  | Instrument spec. | D/C | Instrumentation inter skid of compressor and chiller will be based on manufacturer routine design standard for specifications such as material / connection / accuracy and etc.