## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-EL-PY-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1888 |  |  | Transmital Date: 2/21/2023
Document Title: Layout For Cathodic Protection System for Siahmakan Gas Injection |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-EL-TR-1888 |  |  | Transmital Date: 2/21/2023
[5 empty] | CRS No: NISOC-CRS-BK-PPL-PEDCO-320-EL-PY-0003_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به تائید نشدن مدرک محاسبات سیستم حفاظت کاتدی ( نامه شماره 487782 ) توسط اداره خوردگی فلزات ستاد و در نتیجه نامشخص بودن تعداد ترانس رکتیفایرهای بکار رفته در سیستم ، مقتضی است ، این مدرک پس از تائید مدرک محاسبات ، بروز رسانی و جهت بررسی به این امور ارسال گردد . |  | 1401-2294-491306 | 1401/12/23 | لازم بذکر است به روز رسانی مدرک محاسباتی و همچنین مدرک MTO جهت بررسی مدرک فوق ارسال گردید.
2
3
4
5
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: