## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-AR-DW-0012 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2674 |  |  | Transmital Date: 5/1/2024
Document Title: Architectural Detail Drawing For GCS Warehouse |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-AR-TR-2674 |  |  | Transmital Date: 5/1/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0012_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | کد مدرک EL-PY-0008 در فهرست مراجع اصلاح گردد. |  | 1403-2294-84531 | 1403/03/05 | کد مدرک در فهرست مراجع اصلاح گردید.
2 | عطف به بند 5 ریپلای شیت، ترنچ ورودی برق ساختمان از محدوده درب ورودی فضای 101 به داخل ساختمان به همراه داکت بانک مربوطه لحاظ گردد که این امور اعمال نشده است، لذا اصلاح گردد.لازم به توضیح است برای این منظور می بایست در مدارک مرتبط با آن از جمله CY-PY-0002،EL-PY-0008و EL-PY-0005 تغییرات مقتضی اعمال گردد. |  | 1403-2294-84531 | 1403/03/05 | جابه جایی ترنچ مربوطه انجام شده است، و تغییرات در مدارک مذکور اعمال می گردد.
3 | به آگاهی می رساند، مطابق ماده 13 شرایط عمومی پیمان عمومی پیمان تصویب اسناد و مدارک فنی، مهندسی و طراحی از سوی کارفرما، رافع هیچ یک از مسئولیت ها و تعهدات قراردادی پیمانکار نیست، پس از لحاظ موارد فوق، صدور ویرایش AFC این مدرک بلامانع است. |  | 1403-2294-84531 | 1403/03/05 | تغییرات مذکور اعمال گردید و مدرک AFC صادر گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: