## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-MR-0006 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1981 |  |  | Transmital Date: 3/28/2023
Document Title: PMR For Pressure Safety Valves (PSV) |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-1981 |  |  | Transmital Date: 3/28/2023
[5 empty] | CRS No: NISOC-CRS-BK-PPL-PEDCO-320-IN-MR-0006_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدارک MR پس از تولید و نهایی شدن کلیه مدارک مهندسی تفصیلی مربوطه (مانند مشخصات فنی، داده‌برگ ها و MTO ..... ) می‌بایست تولید گردد، زیرا تمامی مدارک مذکور در مورد هر پکیج خرید، می‌بایست با درج ویرایش نهایی و عنوان آن در متن، ضمیمه MRها شوند. |  | 1402-2294-65461 | 1402/02/24 | با توجه به نظر کارفرمای محترم مدرک با توجه به آخرین نسخه مدارک پیش‌نیاز تهیه گردید و در صورت نیاز در مراتب بعدی پروژه ویرایش خواهد شد.
2
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: