## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-MR-0004 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2248 |  |  | Transmital Date: 7/17/2023
Document Title: PMR For ON/OFF & Shutdown Valves |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-2248 |  |  | Transmital Date: 7/17/2023
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-IN-MR-0004_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در بند 5.1.1 ، عبارت QA organization به QA/QC organization تغيير يابد. |  | BK-SUR-ENG-INS-02-08206 | 2023-08-01 | اصلاح گردید.
2 | لغت ''Purchaser" بايستي در قسمت General Definition تعريف گردد. |  | BK-SUR-ENG-INS-02-08206 | 2023-08-01 | اصلاح گردید.
3 | جهت يكسان سازي، لغت Supplier در متون به Vendor تغيير يابد. |  | BK-SUR-ENG-INS-02-08206 | 2023-08-01 | اصلاح گردید.
4 | در بند 6 : عبارت ''CLIENT/EPC CONTRACTOR " به "CLIENT and EPC/EPD CONTRACTOR" تغيير يابد. |  | BK-SUR-ENG-INS-02-08206 | 2023-08-01 | اصلاح گردید.
5 | رديف ذيل به جدول (Vendor Documents Minimum Requirements) Attachments 2اضافه گردد. SAT Procedure |  | BK-SUR-ENG-INS-02-08206 | 2023-08-01 | اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: