## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-MR-0006 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1981 |  |  | Transmital Date: 3/28/2023
Document Title: PMR For Pressure Safety Valves (PSV) |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-1981 |  |  | Transmital Date: 3/28/2023
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-IN-MR-0006_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-02-07378 | 2023-04-11 | ملاحظه گردید.
2 | در صورت تغيير در هر كدام از مدارك پايه در اين مدرك نيز لحاظ گردد. |  | BK-SUR-ENG-INS-02-07378 | 2023-04-11 | ملاحظه گردید.
3 | در بند 6: -دستورالعمل شماره E&C-QC-IN-SP-1 حذف گردد. -بعد از دستورالعمل شماره ICE-EID-MI-SP01-، عبارت Rev01 اضافه گردد. |  | BK-SUR-ENG-INS-02-07378 | 2023-04-11 | اصلاح گردید.
4 | لزوم ارائه مدارك ITP, QCP, MPS توسط سازنده قبل از برگزاري جلسه PIM در مدرك درج گردد. |  | BK-SUR-ENG-INS-02-07378 | 2023-04-11 | در بخش 6 بیان شده است
5 | در مدرك عبارات Vendor Document Index and Schdule و VPIS يكسان سازي شود. |  | BK-SUR-ENG-INS-02-07378 | 2023-04-11 | اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: