## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-PY-0005 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2453 |  |  | Transmital Date: 10/25/2023
Document Title: F&G Location Layout For Process Area |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-2453 |  |  | Transmital Date: 10/25/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-PY-0005_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | پیرو نظرات این امور در نامه 286131 مورخ 1401/08/08 در Area-8 دتکتور FD-8001 به زیر سایبان دیزل ژنراتور جابجا شود. |  | 1402-2294-338206 | 1402/08/23 | مدرک مطابق خواست کارفرما اصلاح و مطابق با مدارک مرجع بروز رسانی و AFC گردید.
2
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: