## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-AR-DW-0009 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2586 |  |  | Transmital Date:02/19/2024
Document Title: Architectural Drawing For CCTV Control Room- Binak DU |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-AR-TR-2586 |  |  | Transmital Date:02/19/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0009_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در نوت نقشه واحد اندازه گیری سانتیمتر ذکر شده اما در پلان واحدها میلیمتر می باشند، اصلاح گردد. |  | 1402-2294-517414 | 1402/12/13 | تمامی واحدها طبق نوت نقشه به سانتیمتر، اصلاح گردید.
2 | به آگاهی میرساند نظر به اینکه مطابق ماده 13 شرایط عمومی پیمان تصویب اسناد و مدارک فنی، مهندسی و طراحی از سوی کارفرما، از هیچیک از مسئولیت ها و تعهدات قراردادی پیمانکار نمی کاهد، در صورت رفع مورد ذکر شده، صدور ویرایش AFC برای این مدرک بلامانع است. |  | 1402-2294-517414 | 1402/12/13 | مدرک AFC صادر گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: