## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-LI-0008 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2612 |  |  | Transmital Date: 3/2/2024
Document Title: F&G Detector List |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-2612 |  |  | Transmital Date: 3/2/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-LI-0008_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بند 1 از R.S. اصلاح نگردیده است. |  | 1402-2294-542156 | 1402/12/27 | مدرک مطابق آخرین نسخه از مدرک F&G Location Layout for Process Area/Building اصلاح و بروز رسانی گردید.
2 | قابل ذکر است مدرک فوق کلاس 3 می باشد اما در نامه ارسالی POI مدرک AFC ذکر شده است. این مورد نیاز به اصلاح دارد. |  | 1402-2294-542156 | 1402/12/27 | مطابق MDL پروژه، مدرک کلاس 1 می باشد که در مرحله نهایی شدن AFC می گردد.
3
4
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: