## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0022 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2714 |  |  | Transmital Date: 6/22/2024
Document Title: Mechanical Data Sheets For Closed Drain Pumps |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-2714 |  |  | Transmital Date: 6/22/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0022_D07 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظر به وظایف و مسئولیتعای کامل مالی/قراردادی پیمانکار EPC/EPD در این مقطع نظر خاصی دیگری در خصوص این مدرک وجود ندارد و پیشبرد گام بعدی مهندسی تفضیلی بلامانع است. |  | 1403-2294-254708 | 1403/07/07 | نقطه نظر کارفرمای محترم مورد تایید می باشد. همچنین به اطلاع می رساند مطابق مدرک calculation pump تایید شده بخش فرایند SUCTION PRESSURE وDISCHARGE PRESSURE به روز رسانی گردیده است.
2 |  |  |  |  | تغییرات مدرک به شرح ذیل می باشد: -مطابق مدرک Hazardous Area Classification نهایی شده IIB به IIA اصلاح گردید. -پیرو کامنت های شرکت محترم پترو ایران موارد ذیل تصحیح شد: 1-COOLING WATER : (Not Available) 2-MAX. ALLOW. SOUND PRESS. LEVEL REQD (6.1.14) 85 @ 1 m 3-DYNAMIC BALANCE ROTOR (6.9.4.4:YES 4-همچنین با توجه به اینکه نوع پمپ تغییر یافته بود نوت های 30 و 31 اصلاح گردید . 5-نوت 33 در خصوص تست های مربوطه اضافه گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: