## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-MR-0004 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2756 |  |  | Transmital Date: 8/18/2024
Document Title: PMR For On/off & Shutdown Valves |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-2756 |  |  | Transmital Date: 8/18/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-MR-0004_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به عدم نهایی شدن مدرک دیتاشیت، لازم است پیمانکار پس از نهایی شدن مدرک یاد شده از از جانب کارفرما، براساس آخرین ویرایش دیتاشیت نسبت به پیشبرد امور و تهیه TBE اقدام نماید. |  | 1403-2294-223827 | 1403/06/13 | مدرک Datasheet for On/off & Shutdown Valves قبل تر نهایی شده است و به ضمیمه این مدرک ارسال گردید.
2
3
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: