## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-TB-0009 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2765 |  |  | Transmital Date: 8/28/2024
Document Title: TBE For Centrifugal Pumps For Process Services |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-2765 |  |  | Transmital Date: 8/28/2024
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-TB-0009_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
General comment :
1 | در جدول TBE اطلاعات بصورت كامل تر درج گردد.براي مثال SITE CONDITION , SCOPE OF SUPPLY و SCOPE OF WORK بصورت كامل آورده شود.همچنين اطلاعاتي از قبيل Delivery time , Inspection & test , اطلاعات كامل فرايندي و مشخصات درايور ، كوپيلينگ و سيستم آببند در جدول آورده شود. |  | BK-SUR-ENG-MEC-03-09533 | 2024-09-14 | در ویرایش جدید SITE CONDITION ، اطلاعات کامل فرآیندی ومشخصات موتور اضافه شده است و باقی موارد در مدرک موجود می باشد.SCOPE OF SUPPLY و SCOPE OF WORK مطابق مدرک MR می باشد. همجنین Inspection & Test مطابق نوت دیتاشیت پمپ های پروسسی در جلسه PIM نهایی خواهد شد
2 | *No deviation can be checked except those mentioned in Deviation list |  | BK-SUR-ENG-MEC-03-09533 | 2024-09-14 | Noted
Mechanical comments :
1 | ASK : TECHNICAL SPECIFICATION : 1- PAGE 6 OF 88 : SCOPE OF SUPPLY : All motor junction boxes complate with necessary terminal shall be supply by vendor 2- PAGE 11 OF 88 : DEVIATION LIST : Item 1 : Material shall be guaranteed by vendor for pump's condition Item 2 : Accepted except for shaft which shall be concidered EN 10204 3.1 Item 18 : - According to Attachment 11 of Project Basic Document 2 years spare part - price shall be valid up to 6 month after P.O Item 24 : Contrary flange shall be supplied by vendor with respect to pump and related pipe specification 3- PAGE 27 of 88 : Sub vendor list : All sub vendors shall be select from AVL,Also all part of mechanical seal and Flush plan shall be supplied from AVL 4- Data sheet : - PAGE 31 OF 88 : Note 29 : all attached documents to MR shall be submitted to vendor by contractor and vendor shall be signed & stamped it. - PAGE 33 OF 88 : NPSHA shall be specified with respect to pump length , so clarify how much is it ? 3.1? - PAGE 33 OF 88 : PERFORMANCE : To clarify how much is MIN FLOW?2 or 4 ? - PAGE 34 OF 88 : according to API 610 : MAWP shall be at least 40 barg @ 38 - NPSH margin at end of curve shall be added 5-PAGE 66 OF 88 : spare part list shall be in compliance with binak project spare part list 5- NPSH Margin at end of curve shall be compared |  | BK-SUR-ENG-MEC-03-09533 | 2024-09-14 | ASK : TECHNICAL SPECIFICATION : 1- PAGE 6 OF 88 : SCOPE OF SUPPLY : Noted and confirmed, please be noted, LCSs and control panels of motors are not our scope. 2-PAGE 11 OF 88 : DEVIATION LIST : 1-Noted, material selection is not our scope. 2-Noted and confirmed for shaft without original certificate. 18-Noted, Project spare part scope has been already followed, if you have any comment please inform us. -Noted, if spare parts is optional, the price can not valid up to 6 months. 24-Noted, contrary flange will be supplied by ASK and mating flange or reducer shall be provided by purchaser. 3- PAGE 27 of 88 : Sub vendor list: Confirm 4-Data sheet : -Noted, signed and stamped MR and its attachments have been already sent at previous stage. -Noted, NPSHa is 3.1 m. -Noted, Acc. to requested head and suction pressure, reported MAWP is suitable, acc. to API610 standard, MAWP for VS6 type pump @ normal condition is 20 barg @ 38C. -Noted, pump min. continues stable flow is 4 m3/hr. -Noted, NPSHr @ end of curve is lower than NPSHa, this matter has been already specified in the performance cuve, NPSHmargin @ end or curve is 1.77 m -Noted, project spare part scope has been already considered by ASK, if you have any comment please inform us. 5-NPSH Margin at end of curve shall be compared: Noted, NPSHr @ end of curve for all pumps is lower than NPSHa.
2 | Berkeh : -Data sheet for P-2101 A/B : 1- according to API 610 : MAWP shall be at least 40 barg @ 38 C & HYDROTEST shall be 1.5 MAWP barg @ 38 C 2- to check Nameplate power. 3- Data sheet shall be completely filled or confirmed by vendor 4- NPSH margin at the end of curve shall be added and compared -Data sheet for P-2202 A/B : 1-HYDROTEST shall be 1.5 MAWP barg @ 38 C 2- Data sheet shall be completely filled or confirmed by vendor 3- NPSH margin at end of curve shall be added -Data sheet for P-2201 A/B : 1- according to API 610 : MAWP shall be at least 40 barg @ 38 C & HYDROTEST shall be 1.5 MAWP barg @ 38 C 2- Data sheet shall be completely filled and confirmed by vendor 3- NPSH margin at end of curve shall be added -DEVIATION LIST : ROW 1 : NOT ACCEPTABLE ROW 2 : BOM shall be submitted in sectional drawing ROW 4 : Material shall be guaranteed by vendor for pump's condition -Spare part list : spare part list shall be in compliance with binak project spare part list -QC & ITP :After p.o , ITP shall be finalaized in PIM -Sub supplier list : All sub vendors shall be select from AVL |  | BK-SUR-ENG-MEC-03-09533 | 2024-09-14 | Berkeh : -Data sheet for P-2101 A/B : 1- Confirmed 2- will be revised at next revision 3- confirmed 4- Margin is 1.9 m -Data sheet for P-2202 A/B : 1- Confirmed 2- confirmed 3- margin is 1.9 m -Data sheet for P-2201 A/B : 1- Confirmed 2- confirmed 3- margin is 1.4 m -DEVIATION LIST : 1- با توجه به اینکه نقشه های ساخت جزء دانش شرکت می باشد امکان ارائه آن نمی باشد و نقشه های نصب نهایی، انفجاری تحویل خواهد شد 2- نقشه انفجاری تحویل خواهد شد 4-متریال تحت گارانتی می باشد اما انتخاب مواد با شرکت برکه نمی باشد و در این رابطه مسئولیتی ندارد -Spare part list : Confirm -QC & ITP : Confirm -Sub supplier list : Confirm
3 | PETCO : -Data sheet for P-2101 A/B : 1- Vendor shall confirm notes 2- according to API 610 : MAWP shall be at least 40 barg @ 38 C 3- Data sheet shall be completely filled and confirmed by vendor 4- NPSH margin at end of curve shall be added -Data sheet for P-2201 A/B : 1-Page 3 of 11 : Note 6 : Not acceptable.In according to API 610 , if NPSH margine be less than 1m, NPSH test shall be done. 2- Rated flow is not in allowable range (0.8BEP FLOW < Best efficiency flowrate < 1.1BEP FLOW) of this pump so it is not suitable , clarify 3- according to API 610 : MAWP shall be at least 40 barg @ 38 C 4- Data sheet shall be completely filled or confirmed by vendor 5- NPSH margin at end of curve shall be added -Data sheet for P-2202 A/B : 1- Rated flow is not in allowable range (0.8BEP FLOW < Best efficiency flowrate < 1.1BEP FLOW) of this pump so it is not suitable, clarify 2- Discharge flange shall be at least 1 inch 3- according to API 610 : MAWP shall be at least 40 barg @ 38 C 4- Page 3 of 11 : Note 6 : Not acceptable.In according to API 610 , if NPSH margine be less than 1m, NPSH test shall be done. 5- NPSHR is greater than NPSHA, so it is not acceptable.clarify 6- Data sheet shall be completely filled or confirmed by vendor - Sub supplier list : All sub vendors shall be from AVL - Deviation List : 1- Row 1 : not acceptable |  | BK-SUR-ENG-MEC-03-09533 | 2024-09-14 | PETCO : -Data sheet for P-2101 A/B : Confirmed, will be revised -Data sheet for P-2201 A/B : 1- This is our best offer -Data sheet for P-2202 A/B : 1- This is our best offer 1- This is our best offer 2- Please refer to revised offer at next revision 3- 40 barg is confirm 4-Confirmed, will be sent at next revision 5- Confirmed, will be added at next revision 6- Noted. - Sub supplier list: Confirm - Deviation List : Noted. Please refer to revised offer.
4 | Petro Rahan : - Data sheet for P-2101 A/B : 1- Page 3 of 10 : Note 17 : why Discharge flange is greater than Suction? clarify 2- Page 3 of 10 : Note 25 : Pump Type is VS6, so Barrel length shall be considered.Recheck 3- Data sheet shall be completely filled and confirmed by vendor 4- NPSH margin at end of curve shall be added and compared - Data sheet for P-2202 A/B : 1- Data sheet shall be completely filled and confirmed by vendor 2- Rated flow is not in allowable range (0.8BEP FLOW < Best efficiency flowrate < 1.1BEP FLOW) of this pump so it is not suitable , clarify 3- NPSH margin at end of curve shall be added and compare 4- HYDROTEST shall be 1.5 MAWP barg @ 38 C - Data sheet for P-2201 A/B : 1- Data sheet shall be completely filled and confirmed by vendor 2- Rated flow is not in allowable range (0.8BEP FLOW < Best efficiency flowrate < 1.1BEP FLOW) of this pump so it is not suitable , clarify 3- NPSH margin at end of curve shall be added and compare 4- HYDROTEST shall be 1.5 MAWP barg @ 38 C -Spare part list : spare part list shall be in compliance with binak project spare part list -Sub Vendor : All sub vendors shall be from AVL |  |  | 2024-09-14 | Petro rahan: Noted and confirm, Final technical proposal will be sent before P.O
Electrical comments :
1 | 1- موارد كلي 1-1- توان قيد شده در مدرك ليست بار برق با توان موتورها پيشنهادي سازندگان همخواني ندارد براي مثال موتورهاي 22 و 30 كيلووات براي پمپ Slug توسط سازندگان پيشنهاد شده اما در مدرك ليست بار برق براي اين پمپ موتور 15 كيلو وات در نظر گرفته شده است. لازم است BHP و توان نامي موتور در مدرك ليست بار برق بر اساس ماكزيمم پيشنهاد سازندگان اصلاح گردد. 1-2- نيازمندي پروژه براي رديف هاي 5.10 و 6.10 از جدول TBE مطابق مدارك مكانيكال ديتا شيت پروژه به صورت Zone I, IIB, T3 است كه گروه گازي به اشتباه IIA قيد شده و بايستي اصلاح گردد. 1-3- بمنظور يكسان سازي موتورهاي پروژه و انطباق گروه گازي موتور هاي ضد انفجار با نيازمندي خواسته شده در مدرك ديتا شيت موتورهاي الكتريكي فشار ضعيف، از سازندگان خواسته شود گروه گازي كليه موتورهاي ضد انفجار را به صورت IIB در پيشنهاد خود بياورند. 1-4- ديتا شيت موتورهاي الكتريكي فشار ضعيف موجود در پيوست MR باييستي توسط سازندگان تكميل و مهر و امضا شده در پيشنهاد فني ارائه گردد. 1-5- كليه تستها وبازرسي ها با توجه به دستور العمل بازرسي و خريد كالا موجود در پيوست MR در جلسه PIM نهايي خواهد شد. |  | BK-SUR-ENG-MEC-03-09533 | 2024-09-14 | 1-موارد کلی 1-1 مورد تایید می باشد 1-2 گروه گازی مطابق مدارک پروژه IIA می باشد آریا سپهر کیهان: 1-3 ) ملاحظه شد و در ویرایش جدید پیشنهاد فنی در نظر گرفته خواهد شد. 1-4)ملاحظه شد، از آنجایی که کلیه مشخصات و جزئیات موتورها پس از سفارش گذاری توسط تامین کننده مشخص می شود بنابراین این مورد پس از سفارش الکتروموتورها توسط تامین کننده تکمیل خواهد شد. 1-5)3- ملاحظه شد و مورد تایید است برکه: موارد 3-1، 4-1، 5-1 توسط شرکت برکه مورد تایید می باشد پتکو: 3-1) مورد تایید می باشد / 4-1) پس از قرارداد/ 5-1) مورد تایید می باشد. پترورهان: تمامی موارد توسط شرکت پترو رهان مورد تایید می باشد.
2 | 1- آريا سپهر كيهان (پمپ هاي فرآيندي) 1-1گروه گازي موتور پمپ Slug به صورت IIB پيشنهاد گردد. 1-2 گواهي نامه هاي IP و گواهي نامه هاي ضد انفجار براي موتورها بايستي به مدارك ليست شده در بخش 6 مدرك technical specification موجود در پيشنهاد فني اضافه گردد. 2- بركه (پمپهاي فرآيندي) 2-1 گروه گازي موتور پمپ Slug به صورت IIB پيشنهاد گردد. 2-2 فن خنك كننده بعنوان لوازم يدكي دوسالانه موتور اضافه گردد. 2-3 در جدول يك از مدرك Scope of supply موجود در پيشنهاد فني كليه پمپهاي مورد درخواست MR با مشخصات كامل اضافه شوند. 2-4 مشخصات كامل موتورهاي ضد انفجار شامل Zone، درجه حفاظت ضد انفجار (EX’d’) گروه گازي و كلاس حرارتي و درجه حفاظت IP براي كليه موتورهاي پيشنهادي بايستي در پيشنهاد فني آورده شود. 3- PETCO (پمپهاي فرآيندي) 3-1 در پيشنهاد مالي بدون قيمت، درجه حفاظت ضد انفجار براي موتور پمپ Slug به صورت Zone 2, Ex’e’, IIA, T3 پيشنهاد شده است كه بايستي به صورت Zone 2, Ex’d’, IIB, T3 اصلاح گردد. 4- پترو روهان (پمپهاي فرآيندي) 4-1 فن خنك كننده بعنوان لوازم يدكي دوسالانه موتور اضافه گردد. 4-2 مشخصات موتورهاي پيشنهادي شامل درجه حفاظت IP و درجه حفاظتي ضد انفجار، گروه گازي و كلاس حرارتي بايستي صراحتا در پيشنهاد قيد گردد. |  | BK-SUR-ENG-MEC-03-09533 | 2024-09-14 | 1-آریا سپهر کیهان: 1-1 ملاحظه شد و مورد تایید است. 1-2ملاحظه شد و مورد تایید است، این مورد در پیشنهاد مالی لحاظ خواهد شد. 2-برکه: تمامی موارد توسط شرکت برکه مورد تایید می باشد. 3-پتکو: مورد تایید می باشد 4- پترو رهان: 4-1 مورد تایید می باشد 4-2 مورد تایید می باشد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature | H.Naserizadeh |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: