## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-TB-0010 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2765 |  |  | Transmital Date: 8/28/2024
Document Title: TBE For Centrifugal Pumps For General Services |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-2765 |  |  | Transmital Date: 8/28/2024
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-TB-0010_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
General comment :
1 | در جدول TBE اطلاعات بصورت كامل تر درج گردد.براي مثال SITE CONDITION , SCOPE OF SUPPLY و SCOPE OF WORK بصورت كامل آورده شود.همچنين اطلاعاتي از قبيل Delivery time , Inspection & test , اطلاعات كامل فرايندي و مشخصات درايور ، كوپيلينگ و سيستم آببند در جدول آورده شود. |  | BK-SUR-ENG-MEC-03-09533 | 2024-09-14 | در ویرایش جدید SITE CONDITION ، اطلاعات کامل فرآیندی و مشخصات موتور آورده شده است . SCOPE OF SUPPLY و SCOPE OF WORK مطابق مدرک MR می باشد. همجنین Inspection & Test در جلسه PIM نهایی خواهد شد. باقی اطلاعات در جدول TBE موجود می باشد .
2 | *No deviation can be checked except those mentioned in Deviation list |  | BK-SUR-ENG-MEC-03-09533 | 2024-09-14 | Noted
Mechanical comments :
| ASK : TECHNICAL SPECIFICATION : 1- PAGE 6 OF 88 : SCOPE OF SUPPLY : - All motor junction boxes complate with necessary terminal shall be supply by vendor - scope of work of Instrumentation including wiring from MCC to Main motor to be clarified 2- PAGE 11,12,13 OF 88 : DEVIATION LIST : Item 1 : Material shall be guaranteed by vendor for pump's condition Item 2 :Not Accepted. In according to project document(SPECIFICATION FOR CENTRIFUGAL PUMPS FOR GENERAL SERVICES) all mechanical seal shall be in accordig to API 682. Item 3 : Accepted except for shaft which shall be concidered EN 10204 3.1 item 4 & 6 & 12 & 14 : Not nessesary, clarify Item 5 & 7 & 10 & 15:To Note that contrary flange shall be selected by respect to pump and related pipe specification. Item 9 : Explain the reasons of changing Item 11 : After deciding on item 9 item 18 : Not Accepted. In according to project document(SPECIFICATION FOR CENTRIFUGAL PUMPS FOR GENERAL SERVICES), Coupling shall be of stainless steel flexible element with steel coupling hubs provided with spacer. 3- PAGE 29 of 88 : Sub vendor list : All sub vendors shall be from AVL.Also all part of mechanical seal and Flush plan shall be supplied from AVL 4- Data sheet : - page 34 & 41 & 62 of 100 : Note 5 : Material shall be guaranteed by vendor for pump's condition - page 34 & 41 & 62 of 100 : Note 6 : Not Accepted. In according to project document(SPECIFICATION FOR CENTRIFUGAL PUMPS FOR GENERAL SERVICES), Mechanical seal shall be as per API 682 -Page 34 & 41 & 62 of 100 : Note 13 : Note contrary flange shall be selected by respect to pump and related pipe specification. - PAGE 36 & 43 & 57 & 64 OF 100 : all attached document to MR shall be submitted to vendor by contractor and vendor shall be stamped it. - Page 48 & 55 & 69 of 100 : Note 6 : Material shall be guaranteed by vendor for pump's condition - Page 48 & 55 & 69 of 100 : Note 7 : Not Accepted. In according to project document(SPECIFICATION FOR CENTRIFUGAL PUMPS FOR GENERAL SERVICES), Mechanical seal shall be as per API 682 - Page 50 of 100 : Material is not approved by Client and it cannot be checked.it shall be finalized after Client approval. -Page 64 of 100 : Material : Material of impller and wear rings shal be ASTM A48 Class 30B Page 75 of 100 : Spare part list : spare part list shall be in compliance with binak project spare part list 5- NPSH Margin at end of curve shall be compared |  | BK-SUR-ENG-MEC-03-09533 | 2024-09-14 | ASK: 1- PAGE 6 OF 88 : SCOPE OF SUPPLY : Noted, JB for motors will be supplied by ASK but LCSs and wiring from MCC to electromotors are not our scope, controls are not our scope and wiring just at electro-pumps skid will be considered by ASK 2- PAGE 11,12,13 OF 88 : DEVIATION LIST : -Noted, 1-Noted, material selection is not our scope. 2-Confirmed, API682 will be followed for mechanical seals. 3-Confirmed for shaft without original certificate. 4,6,12,14-Pumps nozzle size or rating is different from piping size, for this matter contrary flange can be considered. 5,7,10,15- Contrary flange will be supplied by ASK and mating flange or reducer shall be provided by purchaser. 9-Pump length is 4m and for reduce of vibration, selected VS1 type pump with 1450 rpm speed is more suitable, VS4 type with 1450 rpm is bigger and has lower efficiency and with 2950 rpm is with more vibration and lower efficiency than VS1 type pump. 11-Noted. 18-Confirmed, API671 standard for coupling will be considered 3- PAGE 29 of 88 : Sub vendor list: Noted, please submit project AVL. 4- Data sheet: -Noted, material selection is chemistry and it is not our scope. -Noted and confirmed, API682 standard for mechanical seals will be followed. -Noted, contrary flange will be supplied by ASK and mating flange or reducer shall be supplied by purchaser. -Noted, signed and stamped MP and its attachments have been already sent at previous stage. -Noted and confirmed, API682 standard for mechanical seals will be followed. -Please specify requested material. -Noted and confirmed, A48 class 30B will be considered at next stage. -Noted, project spare part scope has been already followed, if you have any comment please inform us. Noted, NPSHr @ end of curve for all pumps is lower than NPSHa.
| Berkeh : -Data sheets 1- Data sheets shall be completely filled or confirmed by vendor and pump's related curves shall be supplied. -DEVIATION LIST : ROW 1 : NOT ACCEPTABLE ROW 2 : BOM shall be submitted in sectional drawing ROW 3 : Material shall be guaranteed by vendor for pump's condition ROW 6 : Not acceptable . -Spare part list : spare part list shall be in compliance with binak project spare part list -QC & ITP :After p.o , ITP shall be finalaized in PIM -Sub supplier list : All sub vendors shall be from AVL |  | BK-SUR-ENG-MEC-03-09533 | 2024-09-14 | Berkeh : 1-Data sheets confirm -Deviation list: 1-مدارک شامل نقشه نصب نهایی، نقشه مقاطع پس از ساخت تحویل خواهد شد اما نقشه های ساختی این شرکت جزء دانش فنی شرکت بود و به هیچ عنوان تحویل نخواهد شد 2-Confirmed 3-Confirmed (but not selection) 6-Confirmed -Spare Part List confirm -QC & ITP : confirm -Sub supplier list : confirm
| Berkeh : -Data sheets 1- Data sheets shall be completely filled or confirmed by vendor and pump's related curves shall be supplied. -DEVIATION LIST : ROW 1 : NOT ACCEPTABLE ROW 2 : BOM shall be submitted in sectional drawing ROW 3 : Material shall be guaranteed by vendor for pump's condition ROW 6 : Not acceptable . -Spare part list : spare part list shall be in compliance with binak project spare part list -QC & ITP :After p.o , ITP shall be finalaized in PIM -Sub supplier list : All sub vendors shall be from AVL |  | BK-SUR-ENG-MEC-03-09533 | 2024-09-14 | The answer is according to the paragraph above
| Navid Sahand : Vendor information is not complete and enough.vendor shall submit all required information, e.g catalogues, curves, Drawings, spare part list, TCL, Time schedual, deviation list, QC/QA plan & … so this offer would be rejected. |  | BK-SUR-ENG-MEC-03-09533 | 2024-09-14 | Noted & confirmed.
| Petro Rahan : Data sheet for P-2103 A/B : - material for impller shal be A351/A351M GR CF3. - BEP, MCSF , AOR & POR shall be specified on related curve. - Outlet flange size shall be revised. 1 3/4 inch is not allowed Data sheet for P-2102 : - material for impller shal be A351/A351M GR CF3. - BEP, MCSF , AOR & POR shall be specified on related curve. Data sheet for P-2203 A/B : - Material is not approved by Client and it cannot be checked.it shall be finalized after Client approval. - #150 is for Carbon steel flange according to ASME B16.5 and not applicable for this pump. Data sheet for P-2209 : - Why inlet flang is greater than Outlet? - BEP, MCSF , AOR & POR shall be specified on related curve. - #150 is for Carbon steel flange according to ASME B16.5 and not applicable for this pump. Data sheet for P-2206 : - BEP, MCSF , AOR & POR shall be specified on related curve. - Material is S1 so, material for casing shall be A216/A216M Gr WCB. Data sheet for P-2104 : - BEP, MCSF , AOR & POR shall be specified on related curve. *All Data sheets shall be completely filled and confirmed by vendor -Spare part list : spare part list shall be in compliance with binak project spare part list -Sub Vendor : All sub vendors shall be from AVL |  | BK-SUR-ENG-MEC-03-09533 | 2024-09-14 | Petro Rahan: Noted and confirm
Electrical comments :
| 1- موارد كلي 1-1- توان قيد شده در مدرك ليست بار برق با توان موتورها پيشنهادي سازندگان همخواني ندارد . لازم است BHP و توان نامي موتور در مدرك ليست بار برق بر اساس ماكزيمم پيشنهاد سازندگان اصلاح گردد. 1-2- بمنظور يكسان سازي موتورهاي پروژه و انطباق گروه گازي موتور هاي ضد انفجار با نيازمندي خواسته شده در مدرك ديتا شيت موتورهاي الكتريكي فشار ضعيف، از سازندگان خواسته شود گروه گازي كليه موتورهاي ضد انفجار را به صورت IIB در پيشنهاد خود بياورند. 1-3- ديتا شيت موتورهاي الكتريكي فشار ضعيف موجود در پيوست MR باييستي توسط سازندگان تكميل و مهر و امضا شده در پيشنهاد فني ارائه گردد. 1-4- كليه تستها وبازرسي ها با توجه به دستور العمل بازرسي و خريد كالا موجود در پيوست MR در جلسه PIM نهايي خواهد شد. |  | BK-SUR-ENG-MEC-03-09533 | 2024-09-14 | 1-1: مورد تایید می باشد آریا سپهر: 2-1- ملاحظه شد و در ویرایش جدید پیشنهاد فنی در نظر گرفته خواهد شد 1-3: ملاحظه شد، از آنجایی که کلیه مشخصات و جزئیات موتور ها پس از سفارش گذاری توسط تامین کننده مشخص می شود بتابراین این مورد پس از سفارش الکتروموتورها توسط تامین کننده تکمیل خواهد شد. مورد تایید می باشد 1-4: ملاحظه شد و مورد تایید می باشد.. پترو رهان: تمامی موارد توسط شرکت پترو رهان مورد تایید می باشد. برکه: تمامی موارد توسط شرکت برکه مورد تایید می باشد. نوید سهند: تمامی موارد توسط شرک نوید سهند مورد تایید می باشد.
| 1- آريا سپهر (پمپهاي جنرال سرويس) 1-1 مطابق نقشه Area classification layout پمپهاي P-2203A/B Sump Pumps در ناحيه Zone I قرار دارند و بايستي ضد انفجار با درجه حفاظت Zone 1,Ex’d’, IIB, T3 باشند 1-2 گواهي نامه هاي IP و گواهي نامه هاي ضد انفجار براي موتورها بايستي به مدارك ليست شده در بخش 6 مدرك technical specification موجود در پيشنهاد فني اضافه گردد. 2- بركه (پمپهاي جنرال سرويس) 2-1 مطابق نقشه Area classification layout پمپهاي P-2203A/B Sump Pumps در ناحيه Zone I قرار دارند و بايستي ضد انفجار با درجه حفاظت Zone 1, Ex’d’, IIB, T3 باشند 2-2 درجه حفاظت ضد انفجار براي موتور پمپ 2104 در نقشه installation drawing موجود در پيشنهاد فني آورده نشده است. درجه حفاظت براي اين موتور بايستي EX’d’ باشد. 2-3 مشخصات موتورهاي ضد انفجار شامل Zone درجه حفاظت (Ex’d’) و كلاس حرارتي (T3 or T4) و گروه گازي بايستي در متن پيشنهاد آورده شود. ذكر عبارت كلي "موتور خارجي ضد انفجار" در پيشنهاد مالي بدون قيمت كفايت نمي كند. 3- نويد سهند (پمپهاي جنرال سرويس) 3-1 با توجه به اينكه در پيشنهاد اين شركت فقط ديتا شيت هاي پروژه قرار داده شده و ساير مدارك ضروري از جمله deviation list, spare part list, document list, ITP, QC/QA plan, reference list, scope of work and supply, delivery time, guarantee condition, وجود ندارد لذا اين پيشنهاد قابل بررسي نيست. 3-2 مشخصات كامل موتورها از جمله توان موتور، درجه حفاظت ضد انفجار، گروه گازي، كلاس حرارتي و درجه حفاظت IP بايستي صراحتا در پيشنهاد آورده شود. 3-3 مطابق نقشه Area classification layout پمپهاي P-2203A/B Sump Pumps در ناحيه Zone I قرار دارند و بايستي ضد انفجار با درجه حفاظت Zone 1,Ex’d’, IIB, T3 باشند 4- پترو روهان (پمپهاي جنرال سرويس) 4-1 فن خنك كننده بعنوان لوازم يدكي دوسالانه موتور اضافه گردد. 4-2 مشخصات موتورهاي پيشنهادي شامل درجه حفاظت IP و درجه حفاظتي ضد انفجار، گروه گازي و كلاس حرارتي بايستي صراحتا در پيشنهاد قيد گردد. 4-3 مطابق نقشه Area classification layout پمپهاي P-2203A/B Sump Pumps در ناحيه Zone I قرار دارند و بايستي ضد انفجار با درجه حفاظت Zone 1,Ex’d’, IIB, T3 باشند |  | BK-SUR-ENG-MEC-03-09533 | 2024-09-14 | 1-آریا سپهر(حترال سرویس) -ملاحظه شد و در ویرایش جدید پیشنهاد فنی اصلاح خواهد شد. ملاحظه شد و مورد تایید است این مورد در پیشنهاد مالی لحاظ خواهد شد. 2-برکه: تمامی موارد توسط شرکت برکه مورد تایید می باشد. 3-نوید سهند:1)به پيشنهاد فني اضافه گرديد. 2)مورد تائيد است و در مرحله مناقصه پيش از ابلاغ ارسال مي گردد 3)مورد تایید می باشد. 4- پترو روهان (پمپهاي جنرال سرویس): تمامی موارد توسط شرکت پترو رهان مورد تایید می باشد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.behbahani | Signature | H.Naserizadeh |  |  | Clarified By: M.Fakharian | Signature
| Date: 9/14/2024 |  |  |  |  | Date: