## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-IN-MR-0026-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2506 |  |  | Transmital Date: 22/NOV/2023
Document Title:PMR for IRP Panel |  |  |  |  | PEDCO Tr. No.: |  |  | Transmital Date:
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-MR-0026_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدرک P&ID , GENERAL SPECIFICATION FOR FIELD INSTRUMENTATION I/O LIST به فهرست مدارک مرجع افزوده گردد . درضمن لازم است آخرین ویرایش مدارک مرجع مد نظر قرار گیرند. |  | 02/2294/444469 | 1402/10/30 | اعمال گردید
2 | لیست تجهیزات مورد نیاز در قسمت 5 مدرک درج شود. |  | 02/2294/444469 | 1402/10/30 | به روز رسانی گردید
3 | تجهیزات مورد نیاز این مدرک INTERPOSING RELAY PANEL ( IRP ) می باشد ، بنابراین لازم است عبارت WIRING DIAGRAM FOR از ابتدای عبارت WIRING DIAGRAM FOR INTERPOSING RELAY PANEL ( IRP2 ) در جدول تجهیزات مورد نیاز حذف گردد . |  | 02/2294/444469 | 1402/10/30 | به روز رسانی گردید
4 | از ذکر جزییات فنی تجهیزات در جدول پرهیز شود ، کافی است در قالب ستون توضیحات به مدرک مرجع از جمله دیتا شیت ارجاع داده شود. |  | 02/2294/444469 | 1402/10/30 | از ذکرجزییات فنی تجهیزات در جدول اجتناب شده است و مدارک مرجع در ATTACHMENT 1 ذکر شده است .
5 | دیتا شیت اشاره شده در مدرک مرجع به تایید کارفرما نرسیده است ، لازم است پیش از ارسال مدرک PMR مدارک مرجع آن به تایید نهایی کارفرما رسیده باشد. |  | 02/2294/444469 | 1402/10/30 | به همین صورت لحاظ خواهد شد.
6
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M.Torkaman M.Karimi S.Akbari | Signature |  |  |  | Clarified By: | Signature
Date:06-Dec-2023