## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-IN-MR-0026-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2506 |  |  | Transmital Date: 22/NOV/2023
Document Title:PMR for IRP Panel |  |  |  |  | PEDCO Tr. No.: |  |  | Transmital Date:
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-MR-0026_D00 |  |  | CRS Status: | C2
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
General
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  |  | 2023-12-06 | مسئولیت هر گونه تغییر احتمالی بر عهده این پیمانکار خواهد بود.
2 | با توجه به اينكه مدارك پيش نياز اين مدرك نهايي نشده است، در صورت هر گونه تغيير در اين مدرك نيز بايد منعكس گردد. نهايي شدن اين مدرك منوط به نهايي شدن مدارك پيش نياز مي باشد. |  |  | 2023-12-06 | در صورت هر گونه تغییر در مدارک پیش نیاز ، مدارک مرتبط به روز رسانی خواهد شد.
3 | In part 2 General, Vendor scope of supply is “Interposing Relay Panel (IRP-02) … “ not wiring diagram of this panel. |  |  | 2023-12-06 | لحاظ گردید
3 | مدرک - Specification for distribution and lighting panels در لیست مدارک مرجع درج گردد. |  |  | 2023-12-06 | لحاظ گردید
QC. Comments.
1 | كلمات VENDOR و SUPPLIER در مدرك يكسان سازي شده و مطابق توضيحات بخش GENERAL DEFINITION از كلمه VENDOR استفاده گردد . |  |  | 2023-12-02 | اعمال گردید
2 | توضيح مربوط به "لزوم ارائه مدارك ITP, QCP, MPS توسط سازنده قبل از برگزاري جلسه PIM "در مدرك درج گردد. |  |  | 2023-12-02 | اعمال گردید
3 | در بند 5.1.2 (SPARE PARTS) ، در دو سطر شماره مدرك Project spare part supply procedure ميبايست به صورت صحيح E&C-QC-SP-1 آورده شود. |  |  | 2023-12-02 | اعمال گردید
4 | جهت يكسان سازي در كليه مدارك MR پروژه، نگارش توضيحات بند6 مطابق ذيل انجام گردد: The equipment shall be inspected and tested in accordance with the Inspection &Test plan (ITP) issued by the vendor and approved by the CLIENT and EPC/EPD CONTRACTOR before the award of the order . The Inspection & Test plan (ITP ) shall be at least according to the Commodity Procurement and Manufacturing Inspection Instruction ( Docs .Nos. ICE-EID-MI-SP01-Rev01) , Inspection Level of Commodity and Equipment ( Docs .Nos. ICE-EID-MI-SP02-Rev01) and Data Sheets. The vendor shall in any case conduct all the tests required by contractual documents, specifications, codes and standards, manufacturer standard quality system and keep the relevant documentation. All required manufacturing and function test/inspection also Factory Acceptance Test /Site Acceptance Test and Quality Assurance requirements shall be considered in vendor responsibility as per project specification. |  |  | 2023-12-02 | اعمال گردید
5 | در بند 11 (PRICE BREAKDOWN) ، در ايتمهاي شماره 2و3 شماره مدرك Project spare part supply procedure ميبايست به E&C-QC-SP-1 تغيير يابد |  |  | 2023-12-02 | اعمال گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M.Torkaman M.Karimi S.Akbari | Signature |  |  |  | Clarified By: | Signature
Date:06-Dec-2023