## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-MR-0013_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2566 |  |  | Transmital Date: 6 Feb 2024
Document Title: PMR For Pig Signaler |  |  |  |  | NISOC Tr. No.: |  |  | Transmital Date:
[5 empty] | CRS No: NISOC-CRS-BK-PPL-PEDCO-320-IN-MR-0013_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در مورد مدارک فوق نظر خاصی مطرح نمی باشد. |  | 02/2294/493663 | 1402/11/30 | مدرک مطابق اصلاحات دیگر مدارک PMR پروژه اصلاح و نهایی گردید.
2
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M.Torkaman S.Akbari | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: 20 Feb 2024 |  |  |  |  | Date: