## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-MR-0009_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2465 |  |  | Transmital Date: 5 Nov 2023
Document Title: PMR For Pressure/Diff. Pressure Transmitter |  |  |  |  | PEDCO Tr. No.: |  |  | Transmital Date:
[5 empty] | CRS No: NISOC-CRS-BK-PPL-PEDCO-320-IN-MR-0009_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | عبارت SUB-VENDOR در بخش Definition of Terms درج گردد. |  | 02/2294/358349 | 1402/09/06 | نظر کارفرمای محترم بر روی مدرک اعمال گردید.
2 | لازم است مدارک مرجع قبل از ارسال این مدرک به تایید نهایی برسند. مدرک Hook Up هنوز به تایید نهایی نرسیده است. |  | 02/2294/358349 | 1402/09/06 | مطابق نظر کارفرمای محترم مدرک P&ID در دست اقدام می‌باشد. با توجه به اینکه نظرات کارفرمای محترم بر روی آن مدرک تاثیری بر روی خرید ادوات و تهیه مدرک PMR ندارد، نسخه بروز مدرک تهیه و ارسال گردید.
3 | هنگام ارسال این مدارک برای تایید نهایی می‌بایست ویرایش نهایی مدارک مرجع درج گردد. |  | 02/2294/358349 | 1402/09/06 | مطابق نظر کارفرمای محترم آخرین نسخه از مدارک پیش‌نیاز ضمیمه گردید.
4 | عبارت های if required , if any در کل مدرک حذف گردند. |  | 02/2294/358349 | 1402/09/06 | نظر کارفرمای محترم بر روی مدرک اعمال گردید.
5 | در بخش 11 عبارت other fee حذف گردد. |  | 02/2294/358349 | 1402/09/06 | نظر کارفرمای محترم بر روی مدرک اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: