## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-MR-0009_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2465 |  |  | Transmital Date: 5 Nov 2023
Document Title: PMR For Pressure/Diff. Pressure Transmitter |  |  |  |  | PEDCO Tr. No.: |  |  | Transmital Date:
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-IN-MR-0009_D00 |  |  | CRS Status: | C3
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  |  | 2023-11-19 | ملاحظه گردید.
2 | تگ ادوات یا تعداد آنها در مدرک ذکر گردد. |  |  | 2023-11-19 | با توجه به توافقات پروژه و سایر مدارک PMR تگ ادوات یا تعداد آنها در این مدرک بیان نمی‌گردد و برای اطلاعاتی تکمیلی به دیتاشیت مربوطه مراجعه گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M.Torkaman S.Akbari | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: 19 Nov 2023 |  |  |  |  | Date: