## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ST-CN-0007 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-2705 |  |  | Transmital Date:6/2/2024
Document Title: Calculation Note for Tank Foundation (TK-2301 A/B) |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0073-ST-T-2705 |  |  | Transmital Date:6/2/2024
[5 empty] | CRS No:NISOC-CRS-BK-GCS-PEDCO-120-ST-DW-0024_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 03/2294/144833 | 1403/04/17 | با توجه به اطلاعات دریافت شده از وندور مربوطه ، مدارک بازبینی و تغییرات دفترچه محاسبات اعمال گردید. نقشه ها از نظر ابعادی تغییراتی نداشته و تعداد انکر بولتها از 20 به 24 تغییر یافته است که مدارک مربوطه بحضور تقدیم می گردد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: