## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0011-D05 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2812 |  |  | Transmital Date: 02/NOV/2024
Document Title: Mechanical Data Sheets For Elevated Potable Water Tank |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-2812 |  |  | Transmital Date:02/NOV/2024
[5 empty] | CRS No:NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0011-D04 |  |  | CRS Status: | C1
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | همانگونه که در نامه های شماره 03/2294/229391 و 03/2294/175563 بیان گردید نظر به وظایف و مسئولیت های کامل مالی قراردادی پیمانکار EPC / EPD در این مقع زمانی نظر خاصی دیگری در خصوص این مدرک وجود ندارد و پیشبرد گام بعدی مهندسی تفضیلی بلامانع است. |  | 02/2294/349283 | 1403/09/03 | با توجه به نهایی سازی مدارک فرآیندی و پایپینگی/مدل سه بعدی، دیتاشیت بروزرسانی و مجددا ارسال میگردد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.bavarsad | Signature | H.Naserizadeh |  |  | Clarified By: M.Fakharian | Signature
| Date: 11/4/2024 |  |  |  |  | Date: 12/15/2024