## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0013 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2624 |  |  | Transmital Date: 03/06/2024
Document Title: P&ID - Gas Compression Dehydration Package |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2624 |  |  | Transmital Date: 03/06/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0013_D08 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدرک PID تولید شده در فاز مهندسی تفضیلی مورد تایید این امور می باشد لذا اعمال کلیه نقطه نظرات از سوی کارفرما بر مدرک pid تولید شده از سوی سازنده منتخب مدارک مربوط به سازنده پکیج نمزدا می بایست جایگزین مدرک مزبور گردد. |  | 03/2294/78133 | 1403/02/30 | نوت مربوط به شماره مدرک سازنده در مدرک اضافه گردید و در مرحله AS BUILT نقشه سازنده جایگزین می گردد.
2
3
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date:

## Sheet3
177500