## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PI-PY-0001_D05 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2576 |  |  | Transmital Date: 31/02/1403
Document Title:Unit Plot Plan Drawing |  |  |  |  | PEDCO Tr. No.: |  |  | Transmital Date:31/02/1403
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PI-PY-0001_D05 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | همان گونه که در نامه شماره 02/2294/203718 بیان گردید، با توجه به عدم ارایه این مدرک طی جلسه بررسی مدارک فنی و وجود ایرادات در مدل 3بعدی ارایه شده لذا امکان نهایی سازی و صحه گذاری مدرک وجود ندارد |  | 03/2294/78706 | 31/02/1403 | احتراما مدرکPLOT PLAN نیز طی جلسه MODEL REVIEW 90% ایستگاه تقویت فشار بررسی گردید و کلیه کامنت های دریافتی اعمال گردیده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: