## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0011 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2746 |  |  | Transmital Date: 12/08/2024
Document Title: P&ID - 2nd Stage Gas Compression Air Coolers |  |  |  |  | PEDCO Tr. No.: BK-HD-PEDCO-T-2746 |  |  | Transmital Date: 12/08/2024
[5 empty] | CRS No: CRS-BK-GCS-PEDCO-120-PR-PI-0011-D09 |  |  | CRS Status: C2
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با اعمال نظرات ذیل، مدرک مورد تایید می باشد. شایان ذکر است که مطابق شرایط عمومی پیمان فی ما بین و با توجه به مسئولیتهای مالی-قراردادی پیمانکار، مسئولیت بروز هرگونه اشتباه و تناقض، کمبود اسناد و مدارک فنی و اطلاعات تهیه شده از سوی پیمانکار اعم از اینکه از سوی کارفرما تایید شده و یا نشده باشد بر عهده پیمانکار است. |  | BK-SUR-ENG-PCS-03-09478 | 2024-08-26 | مورد تایید می باشد.
2 | درصد شیب برای خطوط ذکر گردد. شیب خطوط 0023، 0025، 0026 و 0054 |  | BK-SUR-ENG-PCS-03-09478 | 2024-08-26 | درصد شیب برای خطوط موجود تعیین گردید. نشان شیب روی خط 0054 به معنی قرار گرفتن BDV در تاپ لوکیشن می باشد بنابراین نشان شیب به معنای درصد شیب نمی باشد.
3 | مدارک ابزار دقیق مرتبط نظیر I/O، Esd Level hierarchy، Index و... متناسب با تغییرات اعمال شده در این ویرایش از P&ID، به روز رسانی گردد. |  | BK-SUR-ENG-PCS-03-09478 | 2024-08-26 | مورد تایید می باشد.
4 | در صفحه سوم XV-2134 دو بار نمایش داده شده است. |  | BK-SUR-ENG-PCS-03-09478 | 2024-08-26 | مطابق نامه 312755-2291-1403 حذف گردید.
5 | کلیه تغییرات منتج از داده های سازندگان، در ویرایش نهایی مدرک اصلاح گردد. |  | BK-SUR-ENG-PCS-03-09478 | 2024-08-26 | مورد تایید می باشد.
6 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-03-09478 | 2024-08-26 | مورد تایید می باشد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.MALEKI | Signature |  |  |  | Clarified By: | Signature
| Date: 26/08/2024 |  |  |  |  | Date: