## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0008 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2768 |  |  | Transmital Date: 01/09/2024
Document Title: P&ID - 1st Stage Gas Compression Air Coolers |  |  |  |  | PEDCO Tr. No.: BK-HD-PEDCO-T-2768 |  |  | Transmital Date: 01/09/2024
[5 empty] | CRS No: CRS-BK-GCS-PEDCO-120-PR-PI-0008-D09 |  |  | CRS Status: | C1
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با اعمال نظرات ذیل، مدرک مورد تایید می باشد. شایان ذکر است که مطابق شرایط عمومی پیمان فی ما بین و با توجه به مسئولیتهای مالی-قراردادی پیمانکار، مسئولیت بروز هرگونه اشتباه و تناقض، کمبود اسناد و مدارک فنی و اطلاعات تهیه شده از سوی پیمانکار اعم از اینکه از سوی کارفرما تایید شده و یا نشده باشد بر عهده پیمانکار است. |  | BK-SUR-ENG-PCS-03-09538 | 2024-09-15 | مورد تایید می باشد.
2 | تغییر کلاس درج شده در نازل خروجی کولرهوایی به محل Tie-in وروردی منتقل شود و کلاس خط Trimline بر این اساس، اصلاح گردد. |  | BK-SUR-ENG-PCS-03-09538 | 2024-09-15 | مورد تایید می باشد.
3 | بر روی خط تخلیه، شیر یکطرفه بعد از شیر دروازه ای قرار گیرد و تغییر کلاس هم بعد از شیر دروازه ای نمایش داده شود. |  | BK-SUR-ENG-PCS-03-09538 | 2024-09-15 | مورد تایید می باشد.
4 | دلیل تغییر نشانه "V" به "VF" برای مشخص نمودن محدوده سازنده تشریح گردد. |  | BK-SUR-ENG-PCS-03-09538 | 2024-09-15 | با توجه به اینکه علامت اختصاری ونت V می باشد، بنابراین جهت جلوگیری از بروز اشتباه مواردی که در اسکوپ کاری سازنده می باشد با علامت اختصاری VF نشاان داده خواهد شد.
5 | نظرات ذینفع اصلی پروژه در مدرک اعمال گردد. |  | BK-SUR-ENG-PCS-03-09538 | 2024-09-15 | مورد تایید می باشد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Maleki | Signature |  |  |  | Clarified By: | Signature
| Date: 14/09/2024 |  |  |  |  | Date: