## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0007 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2623 |  |  | Transmital Date:03/06/2024
Document Title: P&ID - 1st Stage Gas Compression Compressors |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2623 |  |  | Transmital Date: 03/06/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0007_D08 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | توصیه های مزبوط به صورتجلسه HAZOP کمپرسور ملاک عمل قرار گیرد. |  | 02/2291/35542 | 1403/02/03 | مورد تایید می باشد.
2 | مفاد صورتجلیه مربوط به Purging ردیف های کمپرسور به صورت اتوماتیک بایستی در اصلاح وبازنگری نقشه مذکور مد نظر قرار گیرد. |  | 02/2291/35542 | 1403/02/03 | مطابقه نامه دریافتی از کارفرمای محترم مقرر گردید purge ردیف های کمپرسور یه صورت اتومانبک در نظر گرفته نشود.
3 | نوت 14 در حصوص SIL study می بایست مطابق جلسه SIL study اصلاح گردد. |  | 02/2291/35542 | 1403/02/03 | مورد تایید می باشد.
4 | سایز PSV-2122 در مهندسی تفصیلی 2J3 در نظر گرفته شده است در صورتی که این مهم توسط سازنده کمپرسور 3J4 لحاظ شده است لذا می بایست اصلاح مدرک مطابق محاسبات سازنده صئرت پذیرد. |  | 02/2291/35542 | 1403/02/03 | مورد تایید می باشد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021