## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PI-DW-0003-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1074 |  |  | Transmital Date:1401/03/24
Document Title: Piping Key Plan |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-1074 |  |  | Transmital Date:1401/03/24
[5 empty] | CRS No:NISOC-BK-GCS-PEDCO-120-PI-DW-0003-D01 |  |  | CRS Status: | C2
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | ناحیه بندی گودال سوخت و مشعل به درستی انجام نشده است. |  | 01/2294/135314 | 1401/04/19 | احتراما نقطه نظر اعمال گردید. لازم به توضیح است خطی از پروژه تا گودال سوخت نمی رود و TIE IN مربوطه قبل از گودال است
2 | مرزبندی هر محوطه می بایست به گونه ای باشد که بخشی از یک تجهیز یا سازه در یک محوطه و بخش دیگر در محوطه دیگر قرار گیرد از این رو ضروری است برخی نواحی (AREA ) اصلاح گردد. |  | 01/2294/135314 | 1401/04/19 | احتراما نقطه نظر اعمال گردید.
3 | ابعاد هر محوطه می بایست در جدول درج گردد. |  | 01/2294/135314 | 1401/04/19 | احتراما نقطه نظر اعمال گردید. و سایز برگ هر محوطه به همراه SCALE آن محوطه اضافه گردید.
4 | ساختمان ها و جاده های جدید در محوطه بندی نشان داده شوند. |  | 01/2294/135314 | 1401/04/19 | احتراما نقطه نظر اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date :