## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DT-0001_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2565 |  |  | Transmital Date: 6 Feb 2024
Document Title: Data Sheets For Pressure & Diff. Pressure Gauge |  |  |  |  | NISOC Tr. No.: BK-PEDCO-NISOC-0211-IN-TR-2565 |  |  | Transmital Date: 6 Feb 2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-DT-0001_D03 |  |  | CRS Status: | NC
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در مورد مدرک فوق نظر خاصی مطرح نمی باشد. |  | 02/2294/495502 | 1402/11/30 | مدرک مطابق آخرین P&ID بخش ایمنی اصلاح شد . همچنین سنسور تجهیزات PDG/PG با رنج کاری بالای 1 Bar که بصورت DIAPHRAGM ذکر شده بودند ، مطابق با استاندارد IPS به BOURDUN TUBE اصلاح گردید.
2
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 14 Oct 2023 |  |  |  |  | Date: