## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PI-DW-0004-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1288 |  |  | Transmital Date:1401/05/29
Document Title: A/G Piping Plan |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0105-PI-TR-1288 |  |  | Transmital Date:1401/05/29
[5 empty] | CRS No:NISOC-CRS-BK-GCS-PEDCO-120-PI-DW-0004-D01 |  |  | CRS Status: | C3
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | از آنجا که این مدرک بر اساس خروجی نرم افزار مدلسازی ارائه می شود، لذا پیش نیاز بررسی و تایید آن ارائه مدل سه بعدی سایت است. از این رو ارائه آن یک اقدام زودهنگام مهندسی تلقی شده و قابل بررسی نیست |  | 01/2294/218274 | 1401/06/19 | احتراما نقطه نظر اعمال گردید. و در این مقطع مدارک مدل سه بعدی 90 درصد سایت ارائه شده است
2 | همان گونه که در نامه شماره 01/2294/135314 بیان گردید، ناحیه بندی ارائه شده نیاز به اصلاح دارد. در ضمن تا زمان نهایی نشدن آن مدرک ارائه این مدرک امکان پذیر نیست. |  | 01/2294/218274 | 1401/06/19 | احتراما موارد نامه مذکور در مدرک مربوطه اعمال گردید و مدرکKEY PLAN اصلاح شده برای کارفرما ارسال گردید.
4
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri J.Mousazadeh | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 23.August.2022 |  |  |  |  | Date: 23.August.2022