## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PI-DW-0004-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1288 |  |  | Transmital Date:20-Aug-2022
Document Title: A/G Piping Plan |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0105-PI-TR-1288 |  |  | Transmital Date:20-Aug-2022
[5 empty] | CRS No:PEDCO-CRS-BK-GCS-PEDCO-120-PI-DW-0004-D01 |  |  | CRS Status: | C3
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اينكه تا اين مقطع زماني پيش نيازهاي مربوط به اين مدرك از جمله مدل سه بعدي PDMS و نقشه Plot Plan نهايي نشده است لذا امكان بررسي و اظهار نظر درخصوص اين مدرك در مقطع فعلي وجود ندارد. |  | BK-SUR-ENG-PIP-01-05515 | 2022-08-23 | احتراما در این مقطع مدارک PLOT PLAN و مدل سه بعدی نهایی شده است
2 | در تمامي AREA ها مختصات UTM چهار گوشه ها و Tag No. تمامي شيرآلات و پكيجها و تجهيزات ابزار دقيق نوشته شود . |  | BK-SUR-ENG-PIP-01-05515 | 2022-08-23 | احتراما TAG NO. های شیرالات و پکیج هاو تجهیزات ابزاردقیق اضافه گردید. ضمنا همان طور که مستحضر هستید مدارک واحد PIPING با مختصات LOCAL ارائه می گردد.
3 | در جدول مراجع مدل سه بعدي ايستگاه تقويت فشار بينك به عنوان ريفرنس اضافه گردد. |  | BK-SUR-ENG-PIP-01-05515 | 2022-08-23 | نقطه نظر اعمال گردید.
4 | ساپورتها با تگ مربوطه در نقشه ها مشخص گردد. |  | BK-SUR-ENG-PIP-01-05515 | 2022-08-23 | نقطه نظر اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri J.Mousazadeh | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 23.August.2022 |  |  |  |  | Date: 23.August.2022