## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-LI-0003_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2432 |  |  | Transmital Date: 25-Oct-2023
Document Title: I/O List For ESD Systems |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0208-IN-TR-2432 |  |  | Transmital Date: 25-Oct-2023
[5 empty] | CRS No: NISCO-CRS-BK-GCS-PEDCO-120-IN-LI-0003_D04 |  |  | CRS Status: | C2
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-02-08711 | 2023-11-01 | ملاحظه شد.
2 | مشخصا ذکر شود که پنل کنترلی کمپرسورهای گازی برای هر Train بصورت مجزا ارایه شده است. |  | BK-SUR-ENG-INS-02-08711 | 2023-11-01 | در ستون Service ، عنوان Train به این صورت ذکر شده است. Compressor Train A (C-2101-A)
3 | با توجه به مذاکرات انجام شده، در خصوص ارتباط سیستم های کنترلی پکیج ها و IRP در مدارک وندورهای مربوطه لحاظ گردد. |  | BK-SUR-ENG-INS-02-08711 | 2023-11-01 | ملاحظه شد.
4 | بعد از ارایه مستندات مربوط به پکیج ها مدرک می بایست بروز رسانی گردد و در این مقطع قابل تایید نمی باشد. |  | BK-SUR-ENG-INS-02-08711 | 2023-11-01 | ملاحظه شد. بعد از دریافت مستندات پکیج ها، این اطلاعات توسط وندور سیستم کنترل نهایی خواهد شد.
5 | با توجه به ماهیت مدرک و مذاکرات انجام شده با پیمانکار در خصوص خرید سیستم های کنترل و شمارش I/O ها مدرک ارسال شده است و ‌مسئولیت تمامی موارد با توجه به تایید ذینفع اصلی بر عهده پیمانکار می باشد و نیاز است که این مدرک در طول مهندسی تفصیلی نیز بروز رسانی گردد. |  | BK-SUR-ENG-INS-02-08711 | 2023-11-01 | ملاحظه شد.
6
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date:11 Oct 2023 |  |  |  |  | Date: